## Sheet1
Work Scope | Responsibility | Sreenagar POP | Madaripur POP
Site Survey | Admin
Site Selection / Site Build position Selection | Admin
Aggrement sign | Admin
Site drawing for civil work | P&P
Civil Work Drawing approval | P&P
High level planning | PAD
Passive Planning | PAD
PR | O&M
Civil Work vendor selection | SCM
PO | SCM
Passive Implementation (OH,UG,Vertical) | Imp
3 phase Power Connection | O&M (Vendor)
Civil Works (Tiles,Glass work) | Admin (Vendor)
Civil Work (Dismantle, Paint, Plaster, Wall) | Landowner
DB installation, Power cable pulling | O&M (Vendor)
Generator Room Readiness | Admin (Vendor)
A/C installation | Admin (Vendor)
Grounding | O&M (Vendor)
Ladder Installation | O&M (Vendor)
Power System Installation | P&P
Equipment Installation | Imp
Commissioning & testing | Imp
PAT | O&M
On Air | O&M