## Sheet1 (2)
Meeting Minutes
POP project
Date |  | 31.08.16
Location |  | Khansons (2nd floor outer meeting room)
Meeting Title |  | POP status and upcoming requirements
Agenda |  | Follow up and Catch up on various tasks
Participants |  | OM-2 |  | Abdul Jabbar Kabir, Baniah Nowroz Tilova, Nityananda Ghosh Piash, Abir Hasan, Sabrina Amin
|  | OM-1 |  | Mahibul khan
|  | Planning |  | Md. Azizur Rahman Shumon
|  | UG |  | Sharif Abul Kalam Azad
|  | IT |  | Pranabesh Majumder
|  | IIG |  | Md. Niamul Bashir Talukder
|  | Admin |  | Kazi Sifatul Kabir Shawon
|  | P&P |  | Ashok Kumar Biswas
|  | I&C |  | Ibrahim Sharif
|  | Implementation |  | Mustafa Shahinul Haque
SI | POP NAME |  |  | AGENDA | RESPONSIBLE PERSON (SCL/VENDOR) | DEADLINE | STATUS | REMARKS
1 | Palton |  |  | Generator installation | Ashok Kumar Biswas | 28.09.16
2 | Savar |  |  | Savar to Tangail pop link | S.K Abir Hasan | 26.08.16 |  | Savar POP - Kabirpur PGCB -Tangail PGCB -Tangail POP (high loss found)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
3 | Tangail |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
4 | Shirajgonj |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
5 | Bogra |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | PDB Load increment from 10 kw to 34 kw | Kazi Shawon / Md. Kamal Uddin | 21.08.16 | pending | waiting for management Decision.
6 | Naogaon |  |  | Roxtec installation | Roxtec installation
7 | Rajshahi |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Rajshahi- Naogaon UG link readiness | Sharif Abul Kalam Azad | 26.08.16 |  | 1 SP pending
|  |  |  | Rajshahi- Natore UG link readiness | Sharif Abul Kalam Azad | 26.08.17 |  | 2 SP pending
|  |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash | 09.08.16 | Pending at UG | UG to vertical splicing required
8 | Natore |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash |  | NOK | Dependency on UG (after cable blowing vertical will be done)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
9 | Kustia |  |  | Kushtia- Natore UG link readiness | Sharif Abul Kalam Azad | 25.08.16 |  | 1 SP pending (permission issue)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
10 | Jheniadaha |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
11 | Jessore |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
12 | Khulna |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | PDB Load increment from 25 kw to 34 kw | Kazi Shawon / Tayamun Centre Authority | 3 month | pending | Building Authority will install new sub-station
13 | Benapole |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Grounding Cable dreassing (inside Power room) | Mostafa Kamal / Nayan (United Sysnet) |  |  | a ladder will be installed by P&P
14 | Gazipur, Comilla, Mymensing, Barisal, Faridpur |  |  | On air date | Md. Azizur Rahman Shumon | 01.09.16
15 | Gazipur |  |  | Device plan | Md. Azizur Rahman Shumon | 04.09.16
|  |  |  | High level planning & passive planning |  | 02.09.16
|  |  |  | 3 phase PDB connection | Kazi Sifatul Kabir Shawon |  | Ready | As per the verbal discussion between Anwar Bhai & Musleh Bhai it has been decided that from now on grounding and vertical work (Power & Grounding Cable) will be performed by P&P. Admin will just arrange the commercial conncetion.
|  |  |  | AC installation |  | 2016-09-08
|  |  |  | Handover from admin |  | 2016-09-04
16 | Barisal |  |  | 3 phase PDB connection | Kazi Sifatul Kabir Shawon |  |  | 20 Kw Load with commercial meter available.
|  |  |  | Generator room readiness | Kazi Sifatul Kabir Shawon | 2016-09-30 | pending
|  |  |  | ODF installation | Sharif Abul Kalam Azad | 07.09.16 |  | 1 ×144F, 2× 48F ODF Installation
17 | Comilla |  |  | Generator space availability in existing office | Kazi Sifatul Kabir Shawon |  |  | Survey complete, waiting for management decision.
|  |  |  | Latitude and longitude for new office | Md. Azizur Rahman Shumon | 04.09.16 |  | Position should be in between PGCB and Airtel (practically feasible)
18 | Mymensing |  |  | Grounding and power cable vertical | Kazi Sifatul Kabir Shawon
|  |  |  | Survey report | Sharif Abul Kalam Azad, S.H. Zaman | 02.09.16
19 | DHK-CTG-COX |  |  | Total load | Md. Azizur Rahman Shumon & S. M. Arifinul Karim | 04.09.16
Route details
Latitude and longitude for POP office
POP type
On air date
20 | All POP |  |  | POP vertical cable readiness | Md. Abdullah Al. Mamun, Sharif Abul Kalam Azad, S.H. Zaman |  |  | The responsibility for POP vertical readiness will be based on, if UG will reach before ODF termination, they will keep estimated amount fiber in drum inside POP without cutting then responsible team for vertical and ODF termination will take this fiber for ODF termination. If UG team reach later i.e after ODF temination, then they will find estimated fiber loop inside POP (estimated fiber length will be shared by UG before) from ODF which will take inside Hand hole with fiber cut
21 | All POP |  |  | Handover process | POP team members |  |  | After full handover of any POP (from one team to another) snag issues or any kind of observation should be raised within 48 hours otherwise receiving team will be considered responsible for that snag. Before going to do work in any pop every team has to circulate an email regarding work schedule i.e. time and date of doing work should be shared through mail 48 hours before visiting that pop for work.
SI | Agenda |  | POP location
1 | Dhaka-Benapole |  | Summit Center
Banani (New Mohakhali)
Savar (Existing)
Tangail (Existing)
Shirajgonj (new)
Bogra (Expansion)
Naoga (new)
Rajshahi (Existing)
Nator (new)
Kushtia (Expansion)
Jhinaidha (Expansion)
Jessore (Expansion)
Khulna (Expansion)
Benapole (Expansion)
2 | DHA-CTG-COX (Airtel) |  | Palton_SCL
Eliatganj_A
Comilla_A
Choddogram_A
Feni_A
Shitakundu_A
Chittagong_AK
Shatkania_SCL
Chokoria_SCL
Cox-bazar_1
| DHA-CTG-COX (PGCB) |  | Summit Center
|  |  | Meghnaghat_P | Meghnaghat
Comilla_P/new
|  |  | Feni_P | Feni
|  |  | Hathazari_P | Hathazari
|  |  | Khulsi_P | Khulshi
|  |  | Dohazari_P | Dohazari
|  |  | Chokoria_SCL | Chokoria
|  |  | Cox-bazar_2 | Cox