## O&M-3
WCC Update
SL No. | SCL Subcenter | Vendor Name | Maintenance Area | Telco & Others | Info-Sarker | Provision PR length in Mtr (Jan'18 to Mar'18) as per WCC | WCC completed (Length in Meter) | WCC Pending (Length in Meter) | Last OTDR Date | Last OTDR reading (m) | Sign-Off Status | WCC updating month | Remarks
1 | [10 empty] | 1. SC Head Done 2. Regional Head Done 3. Unit Head Done | 2018-01-01
2 | [10 empty] | 1. SC Head Done 2. Regional Head Done 3. Unit Head Done | 2018-01-01 | Full Done
3 | [12 empty] | WCC is on progress
4 | [10 empty] | 1. SC Head Done 2. Regional Head Done 3. Unit Head Done | 2018-01-01 | Telco links WCC done.Info Sarker WCC is on progress
5 | [10 empty] | 1. SC Head Done 2. Regional Head Done 3. Unit Head Done | 2018-01-01 | Here Provision PR length in Mtr (Jan'18 to Mar'18) as per WCC is 369878 which has been given as per old WCC (21st Apr-17) and provision length (Nov-17 & Dec-17). New WCC has been completed at 10th Jan-18. As a result we found this 80270m differences due to Ring modification and UG shifting as per NIP phase-1 project
6 | [12 empty] | WCC is on progress
7 | [12 empty] | WCC is on progress
8 | [10 empty] | 1. SC Head Done 2. Regional Head Done | 2018-02-01 | Full Done
9
10 | [12 empty] | WCC is on progress
11 | [12 empty] | WCC is on progress
12 | [10 empty] | 1. SC Head Done 2. Regional Head Done | 2018-02-01 | Full Done
13
14
15
16
17 | [12 empty] | WCC is on progress,
|  | Total |  |  |  | 0 | 0 | 0

## Summary
Up to date OTDR status of all region for the Year 2018
SL No. | O&M Region | Maintenance Area | Total Maintenance Vendor | Provision PR length in Mtr (Jan'18 to Mar'18) as per WCC | Dec-17 to Jan-18 OTDR Completed (Length in Meter) | OTDR Pending (Length in Meter) | Remarks
1 | O&M-1 | Dhaka Barisal Maymensingh | 17 | 6794872 | 1967038 | 4827834 | OTDR is on pregress for remaining length