## Sheet1
Work Completion Certificate
Date : |  | 2018-01-23
WCC No. : |  | SCL/OM1/SAV/WCC/TELCO/20180123-2
Location of Work : |  | Manikganj Area
Acceptance Type : |  | Payment
Vendor Name : |  | Ideal Cable TV Network
Address : |  | 50 Mymenshingh Road, Banglamotor, Dhaka-1000
Scope of Works : |  | OFC Maintenance at Manikganj Area
SL No | From Location or Site ID | To Location or Site ID | Fiber Type | Activation/Handover Date | OTDR Date | Total Link Length (M) | Share Cable Length (M) | Actual Cable or Billing Length (M) | Span Loss (dB) | Average Loss (dB/Km) | Remarks
22 | MGSBL04 | MGSBL1_HO | 6F Non Messenger | 2017-10-01 | 2017-12-25 | 1609 |  | 1609 | 1.698 | 1.055 | New link
23 | MGSBL04 | MGSB1A_PICO | 6F Non Messenger | 2017-10-01 | 2017-12-25 | 2288 |  | 2288 | 0.610 | 0.267 | New link
Copy:
1. Link Wise OTDR Report
2. Previous WCC Copy
2. Reference Mail Copy for New Handover or Modified Links
| Prepared By |  | Checked By |  | Verifed by |  |  | Recommended By |  |  | Apporved By
| _________________ |  | _________________ |  | _________________ |  |  | ___________________ |  |  | _________________
| Md. Rasel |  | Md. Rasel |  | Suman Nag |  |  | Ahsan Md. Sajid Khan |  |  | Md. Rabiul Alam
| Asst. Engineer |  | Asst. Engineer |  | Deputy Manager |  |  | Sr. Manager |  |  | General Manager
| O&M-1 |  | O&M-1 |  | O&M-1 |  |  | O&M-1 |  |  | O&M-1