## Sheet1
Cross-functional Meeting with Gateway
Date | 2016-09-06 |  | Time | 11:00
Location | L2, NOC Meeting Room
Invitees | Md. Samiul Bashar, A.H.M. Jobayer Shuvo, Kowshik Mushfiqur Rahman, Ashok Kumar
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | ICX device installation at Polton Core | ICX device and rack installation requiremnts at Polton Core will be provided to P&P team. | Jobayer Shuvo | 2016-09-08
2 | Regarding Devie installation Schedule after BTRC visit the Gateway sites | BTRC will visit some of the Gateway sites. Gateway team will finalize their decisions over which devices will they install at those sites BTRC vpaying visit to, and circulate to P&P team along with the installation schedule. | Samiul Bashar | 2016-09-07
3 | DEL Server Installation at Polton Core | Del Server will be installed at Polton Core | Kowshik Mushfiq, Ashok Kumar | 2016-11-08
4 | Required Cable for installation | Required cable by Gateway team will be provided to Kaiser Bhai | Kowshik Mushfiq | 2016-09-08