## Sheet1
MRT Lane_06_update status
SL# | Describe iteam | status | plan Provided date | Update status | Remarks
1 | we have been Provided SCL_Network where it will have impacted by MRT_lane-06 as 7 forwarding letter's | Done | - | done
2 | Claim for compensation for the MRT lane has two phases.. i) Phase #01(Uttara depo to Agargaon) ii) Phase # 02 (Agargaon to Shapla sqr_Motijheel) | Both phases compensation claim has been shared as per DMRT official notifications | - | 1st phase done
3 | Cost analysis and tentative Boq for the Relocations | Done | 25/01/2017 | done
4 | ii) Phase # 02 (Agargaon to Shapla sqr_Motijheel) | BOQ and affected point has been shared with DMRT as letter_05 | Wednesday, ‎August ‎17, ‎2016, ‏‎9:14:55 PM | done
5 | i) Phase #01(Uttara depo to Agargaon)
| Backbone readiness | New HDD: Done | Thursday, August 17, 2017 2:53 PM | done
|  | Cable blowing: done | Thursday, August 03, 2017 3:55 PM | two location pending,Kamal bhai will give update by this week
|  | Backbone Readiness: done | Tuesday, October 31, 2017 10:39 AM | Two location pending,after complete the cable blowing azad Bhai or Arif Bhai will complete the T joint as per provided plan.
|  | Impacted POC/EP published | Thursday, August 03, 2017 3:55 PM | aleady shared with alternate solution
6 | Co ordinate meeting with Underground operation,Marketing,implemenatation and Planning ; regarding issue how to shifting those links. | Impacted clients list shared with KAM : Done | Sunday, August 20, 2017 3:39 PM | already shared
|  | Probable link length(each) share with KAM : Done | Tuesday, September 12, 2017 4:53 PM | Already shared and Kam also align about this issues
7 | Last instruction from DMRT_ for the 1st phase: By end of November_2017 all stake holder will have completed their relocation task as per DMRT Realignment plan. | shifting plan: plan has been provided but not yet executed. | Monday, November 06, 2017 11:08 AM | Ready for Link shifting: Below mentioned station can possible to shifting link gradually….this will require down time align with KAM. - Agargaon station. - Shewra para station. - Mirpur_11 station - Kazipara | Require NCR to shifting those link.