## Sheet1
serial | Priority | agenda | Responsible | dependency/helper | deadline | Everest Remarks
1 | Critical | All NTTN IP device discovered | OSS | O&M | 7th june,10th June
2 | Critical | All NTTN IP device SNMP response | Planning (increase 512k to 2M for ACX 6M for MX) | OSS | 7th june,10th June | Everest team will provide SNMP failed list as of now
3 | Major | All NTTN IP device SSH & Config Mgt | Planning | OSS | 7th june,10th June | Everest team will provide SSH failed list and configure NCM for all IP devices as of now
4 | Critical | All NTTN IP device LLDP enabled | Planning | OSS | 7th june,10th June | Everest team will provide LLDP failed list as of now
5 | Critical | All NTTN IP device Other info | Planning | OSS | 7th june,13th June | Bulk CSV upload
6 | Critical | Huawei IP devices with latest Mib | everest | OSS | 15th June | NCM, Optical TX/RX, Serial & Model of device not updating | See sample
7 | Major | Cisco devices SNMP data correct | Everest | OSS | 15th June | Many interfaces are showing down and up interfaces are giving wrong/same data | See sample
8 | Major | All NTTN IP device SNMP Trap configure | Planning | OSS | 7th june,10th June
9 | Major | Schedule discovery prepare for all | everest | OSS | 15th June | Confirm schedule discovery for all devices Routers+sw
10 | Critical | Garbage Spike in SNMP Data | everest | OSS | 15th June | Deepak will give patch. Confirm time
11 | Critical | False Alarm kill | Everest | OSS | 15th June | Deepak will give patch. Confirm time
12 | Critical | Alarm Dashboard Slowness | everest | oss | Solved | vijay workded twice but yet it got slow again. Need permanent fix
13 | Critical | Huawei MUX devices with NBI | huawei vendor | oss | 12th June | After NBI configuration in Huawei EMS Everest team will integrate NBI
14 | Critical | Tejas MUX device with SNMP & Corba | Tejas | COS |  | After Tejas patch deployment Everest Team need to ensure Performance data for tejas suggested models, topology, alarms for link down etc.
15 | Major | DC Poller Status check Dashboard | Everest | OSS | 15th June
16 | Major | Old Device Data backup | Everest | OSS | 15th June | Deepak will give patch. Confirm time
17 | Critical | Topology Map Rearrange | OSS | PAD,COS | 19th June
18 | Major | Major Backbone Network Diagram : 5 |  |  |  | Everest team will create
19 | Major | Alarm count decrease and old alarm cleanup | everest | OSS | 19th June | Vijay will work with OSS
20 | Major | 172.x.x.x ip dismantle | COS | OSS
21 | Major | Throughput report issue: 1)wrong speed shown 2)interface description 3) down/disable interface not showing | everest | OSS | Solved | Vijay will give patch. Confirm time
22
23