## 13-08-2018
MoM Of Internal Departmental Meeting Of OM-4
S/N | Task | Description | Deadline | Responsible Person
1 | PM, QC, Standardization Activity | PM activity (Passive), standardization works (Passive), Quality control activity (Passive), Support country-wise several issues under BTCL, Teletalk, and Cost minimization activity on passive network | Continue | Md. Rokonuzzaman
2 | GIS data collection | SC wise GIS data collection with proper core information, TJ-box quantity with actual position, E/P and POC quantity with actual position | 31-08-2018 | Suman Nag, Md. Rezaul Karim
3 | Database Update | SC wise site, link, connectivity etc. information update by maintaining proper database | 17-08-2018 | SC Concern
4 | Tangail-Sirajganj (LH) | Findout the most reliable and secure path instead of existing BTCL link with new BL link with the help of NOC database | 14-08-2018 | Suman Nag, Mihir Kumar Bhowmick
5 | Info-Sarker (Phase 2, 3) | Info-Sarker (Phase 2, 3) interface databse update with proper HO information | 19-08-2018 | Suman Nag
6 | Printed Copy of HO Information | Printed HO information and necessery documents of Info-Sarker interfaces | 19-08-2018 | Nityananda Ghosh Piash, Mihir Kumar Bhowmick
7 | Daily Activity Report | Prepare daily activity report with proper responsibilities and activities daily basis by maintaining database in a common folder | Continue | SC Concern
8 | Resources Reqruitment | Resources reqruitment process as per requirement (Tangail: 1 Engineer, 1 Technician, Rajshahi: 1 Engineer, Bogura: 1 Engineer) | Continue | Suman Nag, Mihir Kumar Bhowmick
9 | Weekly Report | Provide weekly report with recursive site/link down issues with action plan, responsibilities information of TT close under all region of OM-4 | Continue | Md. Sajjad Hossain Shihab
10 | LH link update | SC wise all LH link information update | Continue | SC Concern
11 | Vendor Balance | Region wise vendor balance, removal imbalance system, cost minimization activity by ISP lisence provide if reqiured | Continue | Abdul Jabbar Kabir (HoD), Md. Musabbir Choudhury
12 | Telco Issues | Provide weekly basis several telco (BL, GP, ROBI, TBL) issues (Spof, incident root cause etc.) with proper information about client end problem and SCL end problem | Continue | Suman Nag, Md. Rezaul Karim
13 | VT Separation (BL Site) | Maintain VT cable separation works of specially BL sites as per houseowner permission | Continue | Suman Nag, Md. Rezaul Karim
14 | Internal 2nd Line Team | Prepare internal 2nd line operation (IP, SDH, IGW, DWDM etc.) support team under OM-4 for build up new experties | Continue | Md. Musabbir Choudhury, Md. Rezaul Karim
15 | Ignore Mail From Planning Dept. | Ignore the mail from planning department only for new single site addition without any further instructions | Continue | SC Concern
16 | Vendor LD Report | Prepare monthly vendor LD report with proper summery | Continue | Suman Nag, Mihir Kumar Bhowmick
17 | Spare Parts Database | Prepare weekly SC wise spare parts/items (Active and Passive) database under all region of OM-4 | Continue | Md. Rokonuzzaman