## Slide 1
Governance Forum Meeting between Robi & SCL

## Slide 2
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 3
Chart: Site Wise SLA Status(sep’18-Feb’19)
| Sep | Oct | Nov | Dec | Jan'19 | Feb'19
100% | 1620 | 1537 | 1477 | 1541 | 1485 | 1595
99.95% to <100% | 7 | 68 | 51 | 51 | 70 | 25
Below 99.95% | 82 | 104 | 181 | 117 | 154 | 89
Outage Settlement In Progress
Performance Review
Monthly Site SLA Status for 2018 & Jan’19- SLA Maintained
Chart: Robi Network Availability (Sept’18 to Feb’19)
| Sep | Oct | Nov | Dec | Jan'19 | Feb'19
NA (%) | 99.9725 | 99.9747 | 99.9641 | 99.9808 | 99.9628 | 99.9627
SLA (99.95%) | 99.95 | 99.95 | 99.95 | 99.95 | 99.95 | 99.95
Outage Settlement In Progress

## Slide 4
Chart: Site Outage Hour (Including MW site)
| Sep'18 | Oct'18 | Nov'18 | Dec'18 | Jan'19 | Feb'19
2G | 18.4528 | 5.8278 | 13.0771 | 3.6486 | 0.045833 | 9.7542
3G | 21.884 | 94.8965 | 58.0313 | 27.2597 | 87.4861 | 54.9688
Outage Settlement In Progress
Performance Review
Fiber Incident Count & Outage
Chart: Incident Count (SCL)
| Sep'18 | Oct'18 | Nov'18 | Dec'18 | Jan'19 | Feb'19
C-1 | 2 | 3 | 5 | 4 | 7 | 2
C-2 | 7 | 1 | 7 | 3 | 4 | 6
C-3 | 18 | 21 | 36 | 14 | 30 | 37
No Impact | 58 | 33 | 48 | 27 | 57 | 66
 | 85 | 58 | 96 | 48 | 98 | 111
Chart: MTTR (SCL)
| Sep'18 | Oct'18 | Nov'18 | Dec'18 | Jan'19 | Feb'19
C-1 | 0.097569 | 0.042361 | 0.068333 | 0.037674 | 0.070238 | 0.029167
C-2 | 0.084425 | 0.20785 | 0.056448 | 0.086343 | 0.0625 | 0.098148
C-3 | 0.1081 | 0.09602 | 0.15231 | 0.086508 | 0.11671 | 0.15287
No Impact | 0.11675 | 0.30848 | 0.18047 | 0.15391 | 0.1486 | 0.15627
Average | 0.11181 | 0.21911 | 0.15503 | 0.12034 | 0.12973 | 0.14971
YTD avg.
2:07 (Impacting)|| Last year 2:26
3:40 (Non Impacting) || Last year: 4:52
Chart: Site (SCL Base Site) outage hrs with Count
| Sep | Oct | Nov | Dec | Jan'19 | Feb'19
Total outage hours | 338.0383 | 311.9186 | 441.6358 | 236.4553 | 457.7269 | 458.9192
Count | 142 | 363 | 461 | 221 | 375 | 147
Outage Settlement In Progress

## Slide 5
Performance Review
Zone Wise Incident & Outage 2019 (01-Jan’19 to 18-Mar’19)
Dhaka is most impacted in terms of Incident count and outage hour.
CTG is heavily impacted as well.
Chart: ZONE WISE INCIDENT COUNT
| Dhaka North | Dhaka South | CTG | Dhaka Metro | Khulna-Barisal | Mymensingh | Comilla | Rajshahi,Kustia,Rangpur | Sylhet
Count of Incident_ID | 15 | 15 | 17 | 7 | 5 | 13 | 10 | 11 | 2
Sum of Total Outage | 64.5167 | 57.0812 | 35.8083 | 24.5917 | 19.3139 | 15.2361 | 11.8125 | 11.4014 | 2.8611
Chart: Zone wise Outage hour
| Dhaka North | Dhaka South | CTG | Dhaka Metro | Khulna-Barisal | Mymensingh | Comilla | Rajshahi,Kustia,Rangpur | Sylhet
Sum of Total Outage | 64.5167 | 57.0812 | 35.8083 | 24.5917 | 19.3139 | 15.2361 | 11.8125 | 11.4014 | 2.8611

## Slide 6: Performance Review Consecutive 2months repetitive Availability SLA Failed Site of last 3 Months
No of total repetitive availability failed sites : 32
Improvement action taken & resolved : 24
Chart: Zonal distribution of repetitive availability SLA failed site
| Barisal | CTG_North | DHK_Metro | DHK_North | DHK_South | Khulna | Mymensingh
Total | 1 | 3 | 4 | 5 | 15 | 1 | 3
Region | Action Taken | No of Sites
Barisal | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 1
CTG_North | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 1
 | Yet to ensure protection via Robi MW link for some of hill tracts sites | 2
DHK_Metro | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 2
 | Will be solved by 30-Mar'19 | 2
DHK_North | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 5
DHK_South | Fiber path re-route required (after survey deadline will be share) | 3
 | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 11
 | Will be solved by 30-Mar'19 | 1
Khulna | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 1
Mymensingh | Rectification Done and Solved (Non-messenger to messenger shifting, Fiber path reroute, Fiber pull over newly deployed REB poll | 3
InTotal |  | 32

## Slide 7
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 8
Update on Quality Incident
Quality Issues on 01-Jan to 09-Mar,2019 (SCL)
Month | No of Incidents | Total no of impacted Nodes | SCL impacted Base Sites
Jan'19 | 8 | 353 | 138
Feb'19 | 2 | 107 | 34
Mar'19(Till 9th Mar) | 6 | 182 | 24
Grand Total | 16 | 642 | 196
5 Incidents in Gazipur impacting 300 Nodes in total.
2 incidents each for : 10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDR34_102 & 3G_4G_2X10GE_SCL_DRE14_DRH19_DRH21_DRE29_DRE35_GPSDRO5_DHGULO1_184
Chart: Incident Count vs Impacted Node
| Jan'19 | Feb'19 | Mar'19(Till 9th Mar)
No of Incidents | 8 | 2 | 6
Sum of Node Count | 353 | 107 | 182
SCL Base Site Count | 138 | 34 | 24

## Slide 9
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 10: Proactive Action Plan for Network Improvement
Activity | Activity Detail | Impact | Deadline | Status
Backbone Capacity Upgradation | Mymensingh-Gazipur backbone Upgradation 10G to 20G | Backbone capacity upgraded | 9-Mar-19 | Completed
 |  |  | 12-Mar-19 | 
 | Uttara-Pubail & Pubail to Gazipur Upgradation 10G to 100G |  |  | 
 | Vulta-HO upgraded in 100G ring, Comilla region (Comilla, Feni, Chandpur, Laxmipur) 100G upgradation |  | 15-Mar-19 | 
 |  |  | 12-Feb-19 | 
 | Bogra to Nawga BB link Up gradation (10G to 20G) Bogra to Gaibandha BB link Up gradation (10G to 20G) |  |  | 
 | Pubail-DH03-Gazipur link Upgradation 20G to 30G | Backbone capacity upgradation | 30-Mar-19 | On Going
 | Gazipur POP - DH03 new fiber route new BB Link |  | 30-Mar-19 | 
Device Swap | Phase 1: 514 Device swapped with the higher device | High capacity device swapped | - | Completed
 | Phase 2: 46 Device swaped out of 99 device with higher capacity device | High capacity device swapped | 30-Mar-19 | On Going
Access Capacity Upgradation | Phase 1: 306 link’s out of 423 link’s capacity upgradation done from 1G to 10G | Mitigate BW congestion | 30-Apr-19 | Completed
Preventive maintenance | Preventive maintenance for critical site/link [362 out of 390 links done, 243 out of 268 sites done] | PM for summer season | 10-Apr-19 | On Going
Link Rectification | Repetitive Incident Link Rectification [476 out of 624 link done] | To avoid repetitive outage | 30-Apr-19 | On going
Link Shifting | ~2600KM link shifting from Non-messenger OH fiber to newly deployed UG + Messenger fiber [120Km shifted already] | Secured network | 30-May-19 | On Going

## Slide 11
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 12
Update on L2 to L3 Migration
SCL-static 10G Migration-Status
NTTN | Sl # | 10 GE Name | Site Name | Target Timeline | Plan/Execution Date | Status
SCL | 1 | 10GE_SCL_DRE14_DRH19_DRH21_DRE29_DRE35_GPSDRO5_GPSDR34_102 | Dhaka3 | 31/03/2019 | 9/1/2019 | Done
 | 2 | 10GE_CRE13_DRE12_CRE26_CRE27_CMSDR01_FNSDR01_74 | Alekharchor | 31/03/2019 | 25/02/2019 | Done
 | 3 | 10GE_DRE03_DRE11_DRE15_DRE28_NGRPG01_103 | Vulta | 31/03/2019 | 04/03/2019 | Done
 | 4 | 10GE_CRE04_CRE23_CRE24_CRE31_CGDMG29_58 | Akther | 31/03/2019 | 25/03/2019 | WIP
 | 5 | 10GE_RRH17_RPPGN02_01 | Pirganj | 31/03/2019 | 25/03/2019 | WIP
 | 6 | 10GE_RRH09_BOSJP02_54 | Bogra | 30/04/2019 | 01/04/2018 | 
 | 7 | 10GE_KRH08_KHSDR04_13 | Khulna | 30/04/2019 | 08/04/2019 | 
 | 8 | 10GE_GEKRH20_JHSDR06_09 | Hatgopalpur | 30/04/2019 | 15/04/2019 | 
 | 9 | 10GE_BRH18_BSSDR16_06 | Barishal | 30/04/2019 | 22/04/2019 | 
L3 PoP Readiness
Number of PoP | L3 Readiness | Remarks
87 | 80 | Remain 7 will be by 31st April.
Chart: L2 to L3 PoP Traffic Migration Status
| March'19 | April'19 | May'19 | June'19 | July'19 | August'19
 | 29 | 40 | 50 | 60 | 75 | 87
Done

## Slide 13
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 14
EMS/OSS Integration
Robi | SCL
Robi Requested SCL to implement proper EMS/OSS solutions and that is important as their most of 3G/4G network depends on SCL links. In absence of EMS/OSS, difficult to manage :- QoS report(delay, jitter, packet loss etc. Resolution: 15 min/ hourly) Proper link-wise Alarm TT management of SCL links Daily link wise automated outage/downtime/availability report | We are already providing QoS report (delay, jitter, packet loss)daily basis . We are already serving this requirement of ROBI. SCL provided NMS access and 3 training sessions till date at ROBI premises to Robi personnel ( with user manual to ROBI). For Ticketing and NCR tool integration with Robi OSS solution we have communicated and followed up with ROBI for the last three years. All this time we got the same answer from ROBI that vendor is not capable and it involves additional investment from ROBI end. At last ROBI compelled us to use ROBI system rather than handshaking between two company tools for NCR issue. And the access to ROBI system is the most primitive solution which is a remote desktop access to ROBI network to use the web based tool. Till now no progress from ROBI end for TT management. SCL is providing system generated daily report as per ROBI expectation. As per industry standard operator should provide us the daily outage report, but we are helping ROBI doing exception as per ROBI request.
!

## Slide 15
Agenda
Performance Review
Update on Quality Incident
Proactive Action Plan for Network Improvement
Update on L2 to L3 Migration
Contract Amendment
EMS/OSS Integration

## Slide 16
Contract Amendment
QoS KPI and LD mechanism
Robi | SCL
Robi Proposed below Quality KPI with LD mechanism, SCL will share measurement criteria- | SCL previously requested to Robi for base site wise frame loss data and dependent site list for analysis of QoS Proposal. Now Robi asked to explore this data from SCL side. SCL team is working on it.
Alignment and Timeline require from SCL
!

## Slide 17
Contract Amendment
Force Majeure
Robi | SCL
Force Majeure clause was discuss – SCL emphasized that Act of Govt. & Act of God will be consider as Force Majeure and it should written in agreement. Robi proposed below write up- “laws, regulations, and orders of the Government entity having requisite jurisdiction (excluding orders/directions, which are notified earlier by govt. entity and for which there are alternative routes/remedies/resolutions), power failure at national grid [(for continuous period of more than eight (8) hours”. | SCL proposed below write up - “laws, regulations and orders or actions/emergencies thereunder of the Govt. entity having requisite jurisdiction (excluding orders/directions/actions/emergencies of the Govt. entity which are notified earlier by the Govt. entity and for which there are alternative routes/remedies/resolutions), power failure at national grid [for continuous period of more than eight (8) hours”.
Decision- Robi Already aligned with SCL in Internal meeting Considering that SCL will maintain regular patrolling and take proactive action for quick resolutions to avoid LD and force majeure. (Pole shifting , Drainage works, T&T line maintenance should be excluded from force majeure
P

## Slide 18: Contract Amendment -SCL 206 terminated sites
206 terminated sites-
Summary of Discussion till date:
 Robi Feedback: Agreed to keep equipment at AT sites
    SCL Feedback: As these are sites of 3G phase 2, there are no AT sites.
 Robi Feedback: Robi agreed to keep sites required to maintain other Robi sites after SCL provides list.
    SCL Feedback: Robi planning team will validate the list and the space & power cost will be borne by Robi. The Number of sites need to be aligned between both parties.
 Robi Feedback: Robi proposed to dismantle rest of the equipment from e.co sites as these will incur additional cost to Robi for Space & Power. Alternatively, SCL may have separate arrangement with e.co to keep their equipment for their business continuation.
    SCL Feedback: In the last Governance meeting, it was shown as a good gesture from Robi higher management that SCL can keep equipment at the sites. On that notion, we would like to keep our equipment's for another 3 months.

## Slide 19: Contract Amendment -SCL Settlement of 2G agreement
Maximum LD deduction bar
SCL wants maximum 20% bar on LD deduction across all agreements. With other operators, we are practicing significantly lower percentage.
Lock-in period:
Price: 2 years
Service lock-in: 2 years
For up-gradation: 2 years from the date of up-gradation of the particular service. It will be treated as a new deployment
Late payment interest charge:
It was agreed by Robi SCEPMO head that it will be 1.5% monthly but Robi has now changed their stand point to “Bangladesh Bank lending rate”. The issue is still pending.
SCL is practicing 1.5% late payment interest with other operators as well.

## Slide 20: Contract Amendment -SCL Change of Aggregation location (SYSDR01 to SYBLG04)
HO Site SYSDR01 |  | Active Path | Protection Path | Total
Current Scenario | OH (m) | 300 | 300 | 600
 | UG (m) | 600 | 3,500 | 4,100
Total Distance (m) |  |  |  | 4,700
HO Site SYBLG04 |  | Active Path | Protection Path | Total
Proposed Scenario | OH (m) | 18,500 | 7,500 | 26,000
 | UG (m) | 1,100 | 29,900 | 31,000
Total Distance (m) |  |  |  | 57,000
Planned relocation date by the last week of March’19
Power Supply Available: 3rd week of April
Following are the challenges:
Currently SYSDR01 is serving as handover point and termination point of many access ring (30+ sites)
Current handover is fully protected by UG fiber.
  There is no UG presence nearby SYBLG04 (Kurua)
  Full OH solution will be provided (5 poles will be required)

## Slide 21: Contract Amendment -SCL Change of Aggregation location (SYSDR01 to SYBLG04), continued..
Cost incurred by SCL to provision UG for SYSDR01
Investment required to connect SYBLG04
SYSDR01 | Length, m | Total cost
Underground | 4,100 | 4,154,000
Overhead | 600 | 
SYBLG04 | Length, m | Total cost
Underground | 31,000 | 29,980,000
Overhead | 26,000 | 

## Slide 22
Thank you

## Slide 23
Annex

## Slide 24
Repeated Fiber Breaks Jan’2019(SCL)
Link Name | Unit | C-1 | C-2 | C-3 | No Impact | Grand Total
DHKDM42-DHKDM30 | SCL |  |  |  | 5 | 5
NGBND30-NGSDRJ1 | SCL |  |  |  | 5 | 5
DHKDM30-DHSTR68 | SCL |  |  |  | 4 | 4
BOSDR61-BOSDR59 | SCL |  |  |  | 4 | 4
BOSDR59-BOSJP02 | SCL |  |  |  | 3 | 3
DHLLB50-DHSTR68 | SCL |  |  |  | 3 | 3

## Slide 25
Quality Issues on Jan-2019 (SCL)
Incident Date | Impact | Tx Owner | GE/POP | Resolution | Duration
14/1/2019 | HS Frame Loss: 54 Node B | SCL | GE: 3G_4G_10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDRI1_113 | Resolved by SCL | 4:46:13
14/1/2019 | HS Frame Loss: 89 Node B | SCL | GE: 10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDR34_102 | Resolved by SCL | 4:31:38
14/1/2019 | HS Frame Loss: 81 Node B | SCL | GE: 3G_4G_2X10GE_SCL_DRE14_DRH19_DRH21_DRE29_DRE35_GPSDRO5_DHGULO1_184 | Resolved by SCL | 4:11:19
20/1/2019 | Ping Loss: 7 Node B | SCL | PoP: Fenchuganj | Resolved by SCL | 0:22:20
22/1/2019 | High Call Drop: 223 Cells | SCL | GE: 3G_4G_10GE_SCL_DRE03_DRE11_DRE15_DRE28_DRE37_NGRPG01_NGSDRD1_179, 3G_4G_2X10GE_SCL_DRE03_DRE11_DRE15_DRE28_NGRPG01_DHPTN42_111 | Resolved by SCL | 0:58:19
22/1/2019 | High Ping Loss: 81 Node B | SCL |  | Resolved by SCL | 1:46:14
23/1/2019 | Ping Loss: 10 Node B | SCL | PoP: pirojpur | Problem solved from 2019-01-23 11:09:37 BDT. Root Cause - several BB down at Bagerhat area. | 2:28:20
28/1/2019 | High Ping Loss: 8 Node B | SCL |  | Below problem was occurred due to high RSL at DPPBT03 to DPPBT02 link. | 21:15:28

## Slide 26
Quality Issues on Feb-2019 (SCL)
Incident Date | Impact | Status | Tx Owner | GE/POP | Resolution | Duration
11/2/2019 | High call drop: 153 Cells | Closed | SCL |  | SCL TX issue | 3:15:52
20/2/2019 | Fluctuation: 654 Cells | Closed | SCL |  | Found resolved. RCA will share after getting from SCL | 6:11:37
Quality Issues on Mar-2019 (SCL), Till 9th March
Incident Date | Impact | Tx Owner | GE/POP | Resolution | Duration | Impacted Node/Sites | Non Quality Hours
4/3/2019 | HS Frame Loss: 46 Node B | SCL | GE: 3G_4G_2X10GE_SCL_DRE14_DRH19_DRH21_DRE29_DRE35_GPSDRO5_DHGULO1_184 | Resolved by reroute. RCA will share by mail | 19:12:21 | 46 | 883:28:06
6/3/2019 | HS Frame Loss: 30 Node B | SCL | GE: 3G_4G_10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDR34_102 | Issue found resolved previously | 0:24:28 | 30 | 12:14:00
11/3/2019 | High Call Drop: 242 Cells | SCL | GE: 10GE_SCL_CRE13_DRE12_CRE26_CRE27_CMSDR01_FNSDR01_74 | occurred due to high RSL in a link | 19:46:07 | 34 | 672:07:58
11/3/2019 | High Call Drop: 75 Cells | SCL | GE:10GE_ROBI_DRE14_DRH19_DRH21_DRE29_GPSDRO5_30, 10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDR34_102, 3G_4G_10GE_SCL_DRE14_DRH19_DRH21_DRE29_GPSDRO5_GPSDRI1_113 | SCL Tx issue | 5:45:46 | 11 | 63:23:26
12/3/2019 | HS Frame Loss: 44 Node B | SCL | GE: 10GE_SCL_CRE13_DRE12_CRE26_CRE27_CMSDR01_FNSDR01_74 | rectify the LXSDR40 to CP2904 high RSL | 15:43:18 | 44 | 691:45:12
12/3/2019 | HS Frame Loss: 17 Node | SCL | GE: 3G_4G_10GE_SCL_CRE13_DRE12_CRE26_CRE27_CRE30_CMSDR01_FNSDR01_74 |  | 1:17:24 | 17 | 21:55:48