## MoM
MoM: TBL & SCL Meeting
Date: 18 April, 2019 |  | Time: 03:00 PM
Location: Project Office, Teletalk
Participant List: | Md. Dilir Hossain Mollah, Md. Musleh Uddin, Md. Shariful Islam, Md. Abedur Rahman, Md. Farrukh Imtiaz, Jyoti Agarwala
Sajal Kumar Sharma, Sk Barkat Ullah, Prianka Dutta, Aushim Kumar Paul, Saleh Uddin Md. Joni, Md. Omar Farukh
Agenda | Discussion | Responsible | Time Lime
Phase-II Sites | Need to collect the phase-II sites of TBL for taking preparation of implementation | Omar Faruq | Open
Redundant Port Configuration | TBL initiated their requirement for redundant port configuration of E1 services | Prianka Dutta & Aushim Kumar Paul | Open
SDH to IP Migration | TBL has shown their interest to migrate SDH to IP, need to take necessary preparation & plan. | Prianka Dutta & Aushim Kumar Paul | Open
Card Level Redundancy | NCR for ensuring card level redundancy of Mogbazar BTCL (TBL Core) | Sk Barkat Ullah | Done
Up-gradation | 38 nos sites up-gradation delivery timeline | Prianka Dutta & Aushim Kumar Paul | 2019-04-23
SLA | As per TBL requirement, need to revise the SLA for up-gradation | Omar Faruq | 2019-04-25
832 sites status | Need to analyze 832 sites status of TBL | Omar Faruq | 2019-05-02
Power Issue of TBL Sites | Need to share the sites name of power issue with details | Sajal Kumar Sharma | Immidiate Action
Hotline confirmation | Need to confirm after any rectification of TBL site through hotline before leaving site | RIO | Immidiate Action
2G & 3G site status cross check | TBL faces sometimes 2G or 3G down for any particular site but during that time one of any service (2G or 3G) is up. | Sajal Kumar Sharma | Daily
Re-location | Re-location of three TBL sites under CTG region | Nasir Uddin Khan, Aushim Kumar Paul & Omar Faruq | 2019-04-25
CTG Network Topology | TBL initiated their requirement for sharing CTG Network Topology | Mizanul Islam, Jahangir Alam | 2019-05-02
Escalation Matrix | Need to share SCL escalation matrix as per shared format of TBL | Sajal Kumar Sharma | 2019-04-25
Baluns Converter | Ensure availability of Baluns Converter for sub-center for any kind of operational rectification | Sarjana Jahan Chowdhury | Open
Daily Site or Link down analysis | From now SCL & TBL will share a report on daily basis for site or link down issues | Sajal Kumar Sharma | Immidiate Action