## Slide 1
Meeting with Teletalk and SCL
18th April 2019

## Slide 2: Agenda
Timeline for new 46 sites delivery
Card level redundancy for HO sites
Bandwidth up gradation for 93 sites
LTE bandwidth up gradation
Protection path for long haul
SLA for Bandwidth Up gradation
Dedicated POC and Communication Matrix
Total site quantity by cross checking W.O. & P.O.
Root cause for fluctuation of 37 rings.

## Slide 3: Timeline for new 46 sites delivery
Date Wise Delivery | Site Count
Done | 5
4/18/2019 | 1
4/19/2019 | 1
4/20/2019 | 2
4/21/2019 | 1
4/22/2019 | 4
4/23/2019 | 5
4/24/2019 | 4
4/25/2019 | 5
4/26/2019 | 3
4/27/2019 | 5
4/28/2019 | 1
4/29/2019 | 4
4/30/2019 | 5
Grand Total | 46

## Slide 4: Card level redundancy for HO sites
Redundancy ready for Moghbazar HO. SCL inserted the new card dated 15/4/2019 also NCR raised for shifting .But TBL halted the NCR because they have some internal fiber link readiness dependency. New date proposed on 21/4/19.

## Slide 5: Bandwidth up gradation for 93 sites
Total Up gradation from request | Done | Pending | Remarks
93 | 55 | 38 | For 38 sites, SCL need ring re arrangement . Deadline will be shared in next meeting.
Cross checking done and no down gradation done from SCL side. Need further investigation for site wise.
LTE bandwidth up gradation

## Slide 6: Protection status for long haul
Total 23 links (path level) are protected out of 24.
1 link (Dhaka to Manikgonj) is unprotected.
SCL will share deadline for protection on next meeting .
Already shared via mail
SLA for Bandwidth Up gradation
Dedicated POC and Communication Matrix
Site quantity cross check
Total Site Quantity cross checking done and matched with TBL count which is 832
Site Count | IP(hr) | SDH
1 to 10 | 5 | 10
1 to 20 | 10 | 20
1 to 50 | 30 | 60
1 to 100 | 96 | 96

## Slide 7: Root cause for fluctuation of 133 sites in 37 rings.
Problem category | Site count
Power problem | 74
No problem found at that time | 29
BTS end port down. SCL link was ok. | 12
Double fiber break | 12
Traffic Shifting issue (LTE configuration) | 4
One hand power and other hand logical problem | 1
DPDC Pole shifting activity | 1
Chart: Overall Site Status
| TBL side problem | SCL side Problem
Site count | 115 | 18

## Slide 8: Expectation from TBL
Communication matrix from NOC/operation(24/7) for NCR/operational issues.
Site wise POC for power status confirmation & operation issues.
Service status confirmation required immediately while mail reply from SCL.
Smooth access and key support for BTS access.
Need joint visit while BTS port down during no fiber break at SCL end.