## Sheet1
Cross-functional Meeting with Gateway
Date | 2016-09-22 |  | Time | 11:00
Location | L2, NOC Meeting Room
Invitees | Md. Samiul Bashar, A.H.M. Jobayer Shuvo, Rubel Khan, Ashok Kumar, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Regarding New Google Server Installation at Polton PoP | New Google Server will be installed at Polton PoP. After a month of observation the old server will be uninstalled. | Samiul Bashar, Ashok Kumar | 2016-09-30
2 | BD COM Switch installation at Required sites | BD COM switch shall be powered up as per required date at the following sites - Kushtia, Jessore, Faridpur, Benapole, Khulna, Rajshahi, Rangpur etc. | Ashok Kumar, Samiul Bashar | Immediate Action
3 | Cisco Switch Installation at Polton PoP | Cisco Catalist 4500 will be installed at Polton Core | Samiul Bashar, Ashok Kumar | 2016-11-15