## Sheet1
Meeting with Eltek
Date | 2016-09-29 |  | Time | 10:30:00 AM- 12:00:00 PM
Location | L-5 Meeting Room, Khansons Building
Invitees | Md. Musleh Uddin, Md. Rubel Khan, M. Alimuzzaman, Arifin Haque, Khandaker Faysal Ahmed, Sazzad Hossain |  | Attendees | Md. Rubel Khan, M. Alimuzzaman, Arifin Haque, Khandaker Faysal Ahmed, Sazzad Hossain
Sl. No. | Agenda | Description | Responsible |  | Timeline | Remarks
1 | Rectification & Testing | Eltek will take back the delivered Rectifier Systems. After proper rectification & testing, they will return those to SCL. | Sazzad Hossain (Eltek) |  | 2016-10-04
2 | Quality Check | SCL will provide one of their Rectifier to Eltech for quality checking. | Ashok Kumar Biswas (P&P) |  | 2016-10-09
3 | Factory Test Report | Eltek will provide Factory Test Report agaist each Serial Number of Rectifiers. | Sazzad Hossain (Eltek) |  | 2016-10-09