## Sheet1
Cross-functional Meeting Between IT & P&P
Date | 2016-10-02 |  | Time | 3:30:4:00 PM
Location | L5, Meeting Room, Khansons Building
Invitees | Ziaul Hoque, Noman Billah, Toufiq Zaman, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Future Data Space requirement for P&P | Power & Project need more space in file server. They store here Image, auto-cad drawing and other important DOC which is required for site offices. P&P department will provide their requirement space provisioning for next 5 years. | Toufiq Zaman, Umana Rafiq | 2016-10-15
2 | CCTV installation at generator room of remaining sites | P&P will provide the list of sites with generators so that IT can take necessary steps to install CCTV at remaining generator rooms. P&P will also provide the site list for generator installation in future for the same. | Toufiq Zaman, Umana Rafiq | 2016-10-15
3 | Khulna PoP Power Room access control | P&P will inform IT about tentative time of power room shifting at Khulna PoP. IT will provide access to concern P&P engineer to Power Room. | Umana Rafiq, Ziaul Hoque | Open
4 | Ticket Resolving Issue | IT will resolve issues immediately and provide necessary feedback within 30 minutes after raising a ticket. | Ziaul Haque | Immediate Action