## Sheet1
Cross-functional Meeting between Gateway & P&P
Date | 2016-10-04 |  | Time | 11:00-11:30AM
Location | L2, Outer Meeting Room
Invitees | Shahidullah Kaiser, Jobayer Shuvo, Ashok Kumar, Ashim Roy, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Regarding Gateway Device shifting at Benapole PoP | Gateway will complete their device shifting to new location of Benapole PoP. They will install new devices, migrate their traffic to newly installed devices and dismantle the old ones. | Shahidullah Kaiser | 2016-11-20
2 | Google Server Installation at Polton PoP | Google Server will be installed at Polton PoP. P&P team will assign a concern person from their end to complete the activity. | Ashok Kumar, Ashim Roy | 2016-10-10
3 | Del S380 Installation at Uttara PoP | A Del S380 switch will be installed at Uttara PoP. The power requirement for it and required installation date will be informed to P&P dept. | Jobayer Shuvo | Open