## Sheet1
Date | 2016-10-02 |  | Time: 1:00 PM
Location | Khan Son's Building, L5 meeting room
Meeting Title | Cross Departmental Meeting between Implementation and Operations
Agenda | Follow up and Catch up on various tasks
Participants | O&M-1 | Md. Arafat Bin Islam
Zinat Mahzabin
| O&M-2 | Mohammad Musabbir Chowdhury
Rizvina Sultana
| Implementation | Ehsan karim
Md. Ibrahim Sharif
Uttom sharma
Naieem Mahmood Nitul
Sharif Abdul Kalam Azad
Md. Shamsuzzaman
Rakibul Haque
Sl No. | Agenda | Discussion | Responsible | Deadline | Feedback | Status
1 | UG Damage Route | UG implementation will share rest of route shifting from OH to UG which was damaged earlier. | Mr. Zaman & Mr. Kalam Implementation (UG) |  | September 04: PR was rejected (for issue 3, 4, 6, 7). Need to re-submit PR with proper justification. PR submission done for Summit-Vulta backbone.Mr.Ehsan karim will follow up this issue with Business controller department. September 18: All links are in Management Approval list. Permission needed from “ROW”. Corporate Affairs team is taking care of this issue. There is also finical dependency. Mr. Mamun will share the estimated cost for this work with Mahmud sir. September 25: Pending for management approval. October 2: No update , pending at Business controller dept. | Pending
Implementation will work at-
1. Dhaka to Cox's Bazar BKB
2. Gulshan 108 to Pink city
3. Summit-Vulta backbone
4. Bakshibazar to Haronathgosh (Bakshibazar_POC to DHLLB21)
5.Concept furniture hand hole – Back bone down.
2 | Phase-3 Dhaka Metro Status | In your work status mail on 13th May 2016 you mention that, HDD work done for 5 links of Dhaka Metro which was OM requirement. Now almost 1 month left but still cable blowing pending. Note that, these links are very important for us to maintain Dhaka Metro SLA | Mr. Zaman & Mr. Kalam Implementation (UG) |  | September 4, 2016: work done for 4 links out of 5 links. Implementation concern will send handover mail for the 4th link.Other links are pending at business controller dept. end for financial issue. September 18: PR was rejected because it was a claim from MD’s office that two PRs were submitted for this issue & both PRs were same. Implementation team needs to clarify this issue. Mr. Ehsan will collect copy of both PRs and get back to Mahmud sir. September 25: All the documents are escalated to Management. Meeting held on September 22, 2016 regarding this issue with department HOD. Mr. Mustafiz (CA) will share the update of management. October 2: No update, pending at Business controller dept. | WIP
3 | EP to POC conversion | Implementation team needs to share EP to POC conversion schedule. Civil UG team will establish POC box. | UG civil |  | Out of 21 EP, conversion work done for 4, those are AI restaurant, Panthapath, Sonargaon, Hasan Hotel. Tomorrow UG civil team will share the schedule for rest of the EP to POC conversion. September 4, 2016: Business controller dept. didn’t accept the plan for some EPs. They need more business impact information for these EPs.Need to arrange a meeting with HODs to solve this issue. October 2: Many issues are pending at Business controller dept. Need to arrange a meeting with department HOD and Business Controller department. | WIP
4 | FTTB project | At Motijheel area FTTB project could manage permission for 39 buildings and installed 39 building boxes. so Implementation team will install wall mounting enclosure on sunset to make the connectivity from HH/POC to enclosure and to share the clear picture with Marketing KAM for their vetting. | implementation |  | September 25: Pictures were shared but need some changes. New pictures will shared with new format according to Mahmud sir’s instruction. October 2: Frame was prepared as per Mahmud sir’s requirement. Implementation concern shared the picture with marketing team. Now waiting for feedback from marketing team. | WIP
5 | Link Handover | It is proposed by O&M concern that, before a link handover, implementation concern should take client confirmation from Marketing KAM. | Implementation (UG) |  | Implementation team informed marketing kAM about this issue. Marketing KAM agreed to escalate the confirmation notification to Implementation team and O&M team. But marketing KAM didn’t start the practice yet. Implementation team will discuss this issue with marketing team on next cross dept. meeting. September 18: Marketing team didn’t start the practice yet. | Agreed
6 | Duct problem | Implementation team should always connect cable to POC through duct line. If they found any problem in the duct line they should inform O&M concern about it. O&M concern will repair the duct line. | O&M |  | But as per O&M concern person’s observation, implementation team connects cable to POC directly (by not using duct). August 28: Implementation team will escalate list of problematic duct via e-mail. September 4, 2016: Duct problem at Banani road 27, where GP and other clients are connected. Need to open hand hole there for that need to request permission from city corporation. Permission request is already escalated to corporate affairs. | continue
|  | Need to prepare & share Duct list for POC to HH, POC to EP. | Mr. Zaman Implementation (UG) | 2016-10-10 |  | WIP
7 | Plan update | Implementation team should update plan if they make any changes to the network. | Implementation (UG) Mr. Tofazzel | 22-Sep-16 | Implementation team should follow this strictly. Aug 14: Need to do update plan for some links which are already handed over. Aug 28: Plan updated, O&M concern will observe for 2 weeks. September 4, 2016: Need to keep soft copy of all the plans in the common folder. September 18: Implementation team should take acknowledgement from planning team after updating plan. October 2: As per Imp concern, marketing team will share acknowledgement in Excel File. | Closed
8 | Sonargaon 7 to Narayanganj Sadar 29 reroute | Implementation team shared the cable to implement another link where O&M-1 has existing live link Sonargaon 7 to Bandar 10. Implementation team need to reroute the link Sonargaon 7 to Narayanganj Sadar 29. | Implementation | 2016-10-03 | October 2: Cable pulling work done. Shifting work pending. | WIP
9 | 50 Back Haul (Normal fiber replacement by messenger fiber): | Some connectivity was given through normal fiber instead of messenger fiber on emergency basis. Normal fibers should be replaced by messenger fiber. Implementation team needs to share deadline for this issue. | Implementation |  | October 2: Need to discuss this issue with Mahmud sir, Shuvo vaia & Farhan Vaia. | closed
10 | Barishal (BSSDR16-BSBKG05) | Backbone was damaged. Need to do rectification work and 850m cable blowing. | Implementation | 2016-10-15 |  | Open