## Sheet1
Meeting Minutes
POP project
Date |  | 05.10.16
Location |  | Khansons (2nd floor outer meeting room)
Meeting Title |  | POP status and upcoming requirements
Agenda |  | Follow up and Catch up on various tasks
Participants |  | OM-2 |  | Abdul Jabbar Kabir, Baniah Nowroz Tilova, Nityananda Ghosh Piash, Abir Hasan
|  | OM-1 |  | Md. Arafat Bin Islam
|  | Planning |  | S. M. Arifinul Karim, Prianka Datta Suma
|  | ITC |  | Md. Shahidullah Kaisar
|  | SCM |  | Rezaul Haque
|  | UG |  | Md.Shamsuzzaman, Sharif Abdul Kalam Azad
|  | IT |  | Pranabesh Majumder
|  | IIG |  | Md. Niamul Bashir Talukder
|  | Admin |  | Kazi Sifatul Kabir Shawon
|  | P&P |  | Kowshik Mushfiqur Rahman
|  | I&C |  | Arun Roy
|  | Implementation |  | Ehsan Karim, Mustafa Shahinul Haque
SI | POP NAME |  |  | AGENDA | RESPONSIBLE PERSON (SCL/VENDOR) | DEADLINE | STATUS | REMARKS
1 | Palton |  |  | Generator installation | Ashok Kumar Biswas | 01.11.16 | pending
2 | Savar |  |  | Savar to Tangail pop link | S.K Abir Hasan |  |  | Savar POP - Kabirpur PGCB -Tangail PGCB -Tangail POP (high loss found; 30 db loss in 72 km)
3 | Bogra |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan
|  |  |  | PDB Load increment from 10 kw to 34 kw | Kazi Shawon / Md. Kamal Uddin |  | pending | waiting for management Decision.
4 | Naogaon |  |  | Roxtec installation | Roxtec installation
5 | Rajshahi |  |  | Thermal protection | Kowshik Mushfiqur Rahman | 07.10.16
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan
6 | Jhenaidaha |  |  | Thermal protection | Kowshik Mushfiqur Rahman | 09.10.16
7 | Jessore |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan
8 | Khulna |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  | N/A
|  |  |  | PDB Load increment from 25 kw to 34 kw | Kazi Shawon / Tayamun Centre Authority | 3 month | pending | Building Authority will install new sub-station
9 | Benapole |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  | N/A
|  |  |  | Shifting plan and execution | Prianka Datta Suma, S. M. Arifinul Karim, & Abir Hasan | 19.10.16 | pending
|  |  |  | Vertical and ODF installation | Abir Hasan | 20.10.16 |  | 2× 144F ODF
|  |  |  | Grounding Cable dreassing (inside Power room) | Kowshik Mushfiqur Rahman | 22.10.16 |  | a ladder will be installed by P&P
10 | Gazipur |  |  | Device plan | Md. Azizur Rahman Shumon, Prianka Datta Suma, S. M. Arifinul Karim
|  |  |  | Power cable vertical, grounding & power meter installation | S.M Mubasser Hossain | 18.10.16 |  | As per the verbal discussion between Anwar Bhai & Musleh Bhai it has been decided that from now on grounding and vertical work (Power & Grounding Cable) will be performed by P&P. Admin will just arrange the commercial conncetion. (load sangtion done)
|  |  |  | Battery & rectifier installation | Kowshik Mushfiqur Rahman
3 phase connection from substation
|  |  |  | Vertical | Arun Roy & Ibrahim Sharif | 18.10.16
ODF installation
OH cable pulling
11 | Comilla |  |  | Battery and generator space readiness | Kazi Sifatul Kabir Shawon & Rezaul Haque | 26.10.16
12 | Faridpur |  |  | Shifting (execution) | Nityananda Ghosh Piash | 14.10.16
|  |  |  | Generator space plan | Kowshik Mushfiqur Rahman | 06.10.16
13 | Barisal |  |  | Generator room readiness | Kazi Sifatul Kabir Shawon | 9.11.16
14 | Mymensing |  |  | Power cable vertical, grounding & power meter installation | Kowshik Mushfiqur Rahman | 18.10.16
Battery & rectifier installation
3 phase connection from substation
|  |  |  | Vertical | Arun Roy & Ibrahim Sharif |  | pending
|  |  |  | ODF installation |  |  | pending
|  |  |  | OH cable pulling |  |  | pending
15 | DHK-CTG-COX (COX, CTG, Shatkaniya, Chokoria) |  |  | Site survey with checklist | Kazi Sifatul Kabir Shawon | 14.10.16
16 | DHK-CTG-COX (PGCB) |  |  | Site survey with checklist | Abir Hasan & Md. Arafat Bin Islam | 14.10.17 | N/A | 5 previous GP sites in Comilla & 3 previous GP sites in Chittagong
17 | DHK- BEN POP |  |  | Alarm monitoring plan | Kowshik Mushfiqur Rahman | 07.10.16 | on going
18 | All POP |  |  | Existing or upcoming POP UG requirement | Prianka Datta Suma | 09.10.16
19 | All POP |  |  | UG provision in PGCB premises | S. M. Arifinul Karim & Md.Shamsuzzaman
20 | All POP |  |  | POP vertical cable readiness | Md. Abdullah Al. Mamun, Sharif Abul Kalam Azad, S.H. Zaman |  |  | The responsibility for POP vertical readiness will be based on, if UG will reach before ODF termination, they will keep estimated amount fiber in drum inside POP without cutting then responsible team for vertical and ODF termination will take this fiber for ODF termination. If UG team reach later i.e after ODF temination, then they will find estimated fiber loop inside POP (estimated fiber length will be shared by UG before) from ODF which will take inside Hand hole with fiber cut
21 | All POP |  |  | Handover process | POP team members |  |  | After full handover of any POP (from one team to another) snag issues or any kind of observation should be raised within 48 hours otherwise receiving team will be considered responsible for that snag. Before going to do work in any pop every team has to circulate an email regarding work schedule i.e. time and date of doing work should be shared through mail 48 hours before visiting that pop for work.
SI | Agenda |  | POP location
1 | Dhaka-Benapole |  | Summit Center
Banani (New Mohakhali)
Savar (Existing)
Tangail (Existing)
Shirajgonj (new)
Bogra (Expansion)
Naoga (new)
Rajshahi (Existing)
Nator (new)
Kushtia (Expansion)
Jhinaidha (Expansion)
Jessore (Expansion)
Khulna (Expansion)
Benapole (Expansion)
2 | DHA-CTG-COX (Airtel) |  | Palton_SCL
Eliatganj_A
Comilla_A
Choddogram_A
Feni_A
Shitakundu_A
Chittagong_AK
Shatkania_SCL
Chokoria_SCL
Cox-bazar_1
| DHA-CTG-COX (PGCB) |  | Summit Center
|  |  | Meghnaghat_P | Meghnaghat
Comilla_P/new
|  |  | Feni_P | Feni
|  |  | Hathazari_P | Hathazari
|  |  | Khulsi_P/GEC | Khulshi
|  |  | Dohazari_P | Dohazari
|  |  | Chokoria_SCL | Chokoria
|  |  | Cox-bazar_2 | Cox