## MOM 09.10.2016
Date | 2016-10-09
Location | Khan Sons
Meeting Title | Regular Weekly meeting between Implementation and Planning Team
Agenda | Follow up and Catch up on various tasks
Attendees | Implementation |  | Md.Shamsuzzaman
Sharif Abdul Kalam Azad
Abul Kalam
Naieem Mahmood Nitul
Sadaf Md. Zahir
Rakibul Hasan
| Planning |  | Mohebubur Rahman
Nuruzzaman Rasel
Juhi Johana Bashir
Rabeya Anzum
SL No. | Discussion Point | Discussion/Decision | Responsible | Deadline | Status | Remarks
1 | Cable Blowing from Jahangir gate to Proshanti POC | Permission from cantonment board is yet to get. Work will be commenced by respective department after getting permission. | Implementation (Civil & UG) | 8/31/2015, 9/14/2015 10/5/2015 10/19/2015 11/9/2015 12/7/2015, 3/15/16 (no deadline can be set until we get permission) | Open | According to the permission letter that civil team received from cantonment board, All NTTNs have to work at the same time.Therefore permission letter need to revise as per civil team feedback.Corporate Affairs working to get new permission. Alternative solution: Core rearrangement to get free core. Core rearrangement and red limpia both can be performed under same permission. This issue has been escalated to higher management by Ehsan Bhai and subsecuently to cantonment board. Waiting for final feedback from cantonment board.
2 | GP old 100 sites update | Implementation team will share the work status of GP first 100 sites. The project is ongoing. | Implementation | Weekly update | Open | As per last update from I&C team, OH done for 95 sites, vertical done 90 sites, Device deployed in 91 sites and 82 sites incorporated in network and service provisioning done for 58 sites, GP issue 10 sites. PAT done for 48 sites.
3 | UG Network deployment status | UG Network deployment status needs to be updated by UG team within Thursday of every week. Updated file will be provided by UG team. | Implementation (UG & Civil) | Weekly update | Ongoing | Uttom bhai
4 | Bi-weekly UG KMZ and coverage update | UG team will provide KMZ of newly deployed UG network along with Bi-weekly update. UG team will provide the bi-weekly update according to the new format which will be shared by planning team. | Implementation(UG) | Bi-weekly update | Ongoing | Uttom Bhai.
5 | Bi-weekly OH update | OH team will send bi-weekly OH update according to the new format which will be shared by planning team. | OH team | Bi-weekly update | Open | Arun Bhai is getting updates in time
6 | Robi 52 Backhual Update | Implementation team will provide update for device installation,Fiber readiness and service integration of Robi 52 backhaul project in every Sunday. | I&C and OH | 15/10/2016 | Open | 52 sites service provisioning are done out of 52. Protection issue for the last 4 sites is ongoing ( pole installation work is on going )
7 | Update from IMP team for all links as per provided work plan from PAD | PAD will share the provided work plan list weekly with IMP team and IMP team will provide update accordingly. | PAD & IMP | Weekly update | Ongoing | After receiveing any kind of work plan from PAD regarding handover links, IMP team will provide update as per recommended timeline. Also Number of T-joint will be shared with Plan.
8 | IPLC underground readiness Status | 3 out of 15 are completed | IMP (CIVIL UG) | - | Open | civil work has done for 3 links.The rest is pending due to permission issue. IMP team will provide timeline for whole task after getting permission from corporate affairs. Civil team communicated with corporate affairs via mail but did not get any response.
9 | T-joint update after each plan mismatch | Implementation team will provide update for each plan mismatch | IMP | - | On going | -
10 | Timeline required for UG Phase-1,Phase-2 & Phase-3 | UG civil team will Share specific timeline for all links from the existing approval | IMP (CIVIL UG) | - |  | IMP team will provide timeline by 27/09/2016 for the whole task. This issue has been escalated to Mahmud Sir.
11 | Link ID for OH plan | Planning team will provide link ID for the circulated OH plan. | Planning | - | Ongoing | -
12 | Network expansion and modification | Implementation civil team will start working in 10 days after getting permission. 7 days are required for tjoint splicing. | IMP (CIVIL UG) & client | - | on going | -
13 | Barisal UG shifting | Barisal_Zone link shifting from OH to UG | IMP ( Civil ) | 2016-02-10 | closed | Rupatoli to Boyalia Bazer UG cable has damaged.