## Sheet1
Cross-functional Meeting - O&M (PGCB) and P&P
Date | 2016-10-13 |  | Time | 3:00 PM-3:30 PM
Location | L5, Meeting room, Khan Sons Building
Invitees | Mizanul Islam, Abdullah Saleh, Sayda Jahan, Ashok Kumar, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Sirajganj PGCB Space expansion Issue | PGCB team will provide a follow-up regarding Sirajganj PGCB Space expansion issue after the agreement | Mizanul Islalm, Abdullah Saleh | Open
2 | Jessore PGCB civil construction fault issue | P&P concern has raised an issue regarding Jessore PGCB. The room floor shakes whenever a heavy vehicle passes nearby the road which might affect the equipments. PGCB team is informed of the issue and they will take necessary steps to resolve the matter. | Abdullah Saleh, Mizanul Islam, Ashok Kumar | Open
3 | PGCB room renovation | Some of our PGCB sites require room renovations due to damp wall/floor and rust on doors. PGCB team will provide a solution to resolve the issue. | Abdullah Saleh, Mizanul Islam, Ashok Kumar | Open