## Permission status
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Permission | Permission Status | Permission Steps | Remarks
1 | MNRMP1-MNMLK1 | Dhaka | CF | 7.4 | 2000-01-01 | ABM | Done | Pending | 1st | GP will prepare the PO after that Mr. Palash will do the other formalities from SCL end about the billing of this link. Civil work for this link will start after getting the bill. Chairman sir and MD sir will set a meeting with Bridge secretary.
2 | NGTWNR-MNRMP1 | Dhaka | CF | 18.27 | 0-Jan-00 | ABM | Done | Pending | 1st
3 | CMELT2-BMBAN1-NGSON4 | Comilla | 250KM | 31.986 | 0-Jan-00 | SS | Done | Pending | 4th
4 | KSBZPR-KSKAT1 | Kishorgonj | 250KM | 14.783 | 2000-01-01 | Btek | Done | Pending | 6th
5 | MGHCK1-MGDTA1 | Savar, Dhaka | 250KM | 8.452 | 0-Jan-00 | STL | Done | Pending |  | Mr.Mamun got verbal go call from GP. Mr. Mamun will escalate go ahed mail to Mr.Rubayet.
6 | MDTWN5-SPANG1 | Saridpur | 250KM | 14.386 | 0-Jan-00 | Nijum | Done | Pending | 0
7 | SPANG1-SPBDG1 | Saridpur | 250KM | 15.128 | 0-Jan-00 | Hasan | Done | Pending | 4th
8 | BSBOA1-BSBKG1 | Barisal | 250KM | 5.672 | 0-Jan-00 | Hasan | 2016-10-23 | Pending | 1st | Verbal permission done
9 | BMAKAR-BMKUT3-CMMDBR | Comilla | 250KM | 9.857 | 0-Jan-00 | SS | Done | Pending | 5th
10 | GPMNA1-GPSRP1 | Gazipur | 250KM | 8.906 | 0-Jan-00 | Btek | Done | Pending | 0 | Gazipur(Sripur to Mawna)-HDD work done, Handhole work done, cable blowing work ongoing. CA concern Mr. Rubayet will help the vendor Btek to prepare the estimate within the budget 5 Lakh 40 thousand.
11 | PGBDA1-NPBRG1 | Panchogor | 250km | 35 | 0-Jan-00 | Shine | Done | Pending | 4th
169.84
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Permission | Permission Status | Permission Steps | Remarks
1 | SNJAW1-SNMOL1 | Sylhet | 90 KM | 26 |  | NCC | waiting | Pending | 6th
2 | MDSMD1-MDTWN5 | Madaripur | 60 KM | 11.135 |  | STL | waiting | Pending | 0
3 | MYTWNR-MYBOU1-MYPRPR | Mymensing | 250KM | 0.6 |  | Shine | GP | GP |  | GP depended. BD Railway permission needed.
4 | MDTWN5-MDCHLT-SPANG1 | Madaripur | 250KM | 10 |  | STL | waiting | Pending | 0
5 | GPJJR18 – GPSLN1 – GPJDPR1 | Gazipur | 250KM | 7.338 |  | Btek | waiting | Pending | 0 | BD Army permission issue
Note: To make us understand easily about the permission steps CA concern Mr. Rubayet has divided total permission procedure in 6 steps. Stages are given in the next page.

## Permission stages
Sl No | RHD Office | Work Steps | Weight in term of time | No. of Persons sign on every step (Min) | Particulars
1 | Sub Divisional Engineer's Office | Step 1 | 30% | 4 | Maximum documents are collected here, signatory may increase based on length
2 | Executive Engineer's Office | Step 2 | 20% | 4 | Exen got ultimate authority to sign on any document
3 | Superintending Engineer's Office | Step 3 | 10% | 3 | route feasibility checked
4 | Additional Chief Engineer's Office | Step 4 | 10% | 3 | Calculation checked
5 | Chief Engineer's Office | Step 5 | 20% | 6 | Here all the documents are checked
6 | Ministry | Step 6 | 10% | 4 | It takes 7days for approval
|  |  | 100% | 24