## Permission status
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Permission | Permission Status | Permission Steps | Remarks
1 | MNRMP1-MNMLK1 | Dhaka | CF | 7.4 | 2000-01-01 | ABM | Done | Pending | 1st | SCL concern tried to communicate with vendor ADM, but they didn’t respond.
2 | NGTWNR-MNRMP1 | Dhaka | CF | 18.27 | 0-Jan-00 | ABM | Done | Pending | 1st | SCL concern tried to communicate with vendor ADM, but they didn’t respond.
3 | CMELT2-BMBAN1-NGSON4 | Comilla | 250KM | 31.986 | 0-Jan-00 | SS | Done | Pending | 4th | Additional chief engineer was not free due a meeting at Ministry
4 | KSBZPR-KSKAT1 | Kishorgonj | 250KM | 14.783 | 2000-01-01 | Btek | Done | Pending | 6th | Because of 23rd DNCC meeting, joint secretary halts our file till Oct 27, 2016.
5 | MGHCK1-MGDTA1 | Savar, Dhaka | 250KM | 8.452 | 0-Jan-00 | STL | Done | Pending |  | CRA dept. asked to Mr. Mamun that if possible to take alternate route for this link. As per Mr. Mamun alternate route is not possible. CRA need arrange permission for the existing route.
6 | MDTWN5-SPANG1 | Saridpur | 250KM | 14.386 | 0-Jan-00 | Nijum | Done | Pending | 0 | SCL MD's approval needed
7 | SPANG1-SPBDG1 | Saridpur | 250KM | 15.128 | 0-Jan-00 | Hasan | Done | Pending | 4th | Additional chief engineer was not free due a meeting at Ministry
8 | BSBOA1-BSBKG1 | Barisal | 250KM | 5.672 | 0-Jan-00 | Hasan | 2016-10-23 | Pending | 2nd | Additional chief engineer was not free due a meeting at Ministry
9 | BMAKAR-BMKUT3-CMMDBR | Comilla | 250KM | 9.857 | 0-Jan-00 | SS | Done | Pending | 6th
10 | GPMNA1-GPSRP1 | Gazipur | 250KM | 8.906 | 0-Jan-00 | Btek | Done | Pending | 0 | Vendor is asking for 190 tk/m, we don’t comply with that rate.
11 | PGBDA1-NPBRG1 | Panchogor | 250km | 35 | 0-Jan-00 | Shine | Done | Pending | 4th | Additional chief engineer was not free due a meeting at Ministry
169.84
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Permission | Permission Status | Permission Steps | Remarks
1 | SNJAW1-SNMOL1 | Sylhet | 90 KM | 26 |  | NCC | waiting | Pending | 6th | Because of 23rd DNCC meeting, joint secretary halts our file till Oct 27, 2016.
2 | MDSMD1-MDTWN5 | Madaripur | 60 KM | 11.135 |  | STL | waiting | Pending | 0 | SCL MD's concern and MOU with RHD
3 | MYTWNR-MYBOU1-MYPRPR | Mymensing | 250KM | 0.6 |  | Shine | GP | GP |  | GP depended. BD Railway permission needed.
4 | MDTWN5-MDCHLT-SPANG1 | Madaripur | 250KM | 10 |  | STL | waiting | Pending | 0 | SCL MD's concern and MOU with RHD
5 | GPJJR18 – GPSLN1 – GPJDPR1 | Gazipur | 250KM | 7.338 |  | Btek | waiting | Pending | 0 | BD Army permission issue

## Billing Status
S.L | Project | Description | WR length | Billing Status
1 | PTAGR1-PTPNG1 | Patuakhali | 8.175 | 100% Done
2 | PTPNG1-PTTWN1 | Patuakhali | 9.168 | 100% Done
3 | PTTWN1-BRSKB2 | Patuakhali | 6.611 | 100% Done
4 | PTAGR1-PTBRD1 | Patuakhali | 9.312 | 100% Done
5 | PTBOG1-PTAMT1 | Patuakhali | 19.883 | 100% Done
6 | BHCOS1-BHBKH1 | Bhola | 6.16 | 100% Done
7 | SYBSN1-SNSAY1-MBSHE1 | Sylhet | 15.592 | 100% Done
8 | NKDGP3-NKTWNR | Mymensing | 25.82 | 100% Done