## Sheet1
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Work Start Date | Permission Status | Permission Receive Date | Permission septs | Bill Status 30% | Bill Status 70% | Remarks
1 | MDSMD1-GGSTP1-FPBBR1 | Gopalgonj | 60 KM | 17.581 | 100% | SCL | Done | Done | Done |  | Done | Done
2 | BGDBL1-GGSTP1 | Gopalgonj | 60 KM | 33.658 | 100% | SS + MBCC | Done | Done | Done |  | Done | Done
3 | BSCOS1-BSBMHT-BSBOA2 | Barisal | 90 KM | 16.143 | 100% | SCL | Done | Done | Done |  | Done | Done
4 | NPBRG1 - NPTGM2 | Nilphamary | 90 KM | 31.142 | 100% | SCL | Done | Done | Done |  | Done | Done
5 | CGKTGT-HH | Chittagong | 90 KM | 1.65 | 95% | SCL | Done | Done | Done |  | Done | Pending
6 | MNRMP1-MNMLK1 | Dhaka | CF | 7.4 | 100% | ABM | Done | Pending | Pending | 1st | Done | Pending | SCL concern tried to communicate with vendor ADM, but they didn’t respond.
7 | NGTWNR-MNRMP1 | Dhaka | CF | 18.27 | 90% | ABM | Done | Pending | Pending | 1st | Done | Pending | SCL concern tried to communicate with vendor ADM, but they didn’t respond.
8 | MDSMD1-MDTWN5 | Madaripur | 60 KM | 11.135 | 10% | STL | Pending | Pending | Pending | 1st | Done | Pending | Pending for MOU
9 | SNJAW1-SNMOL1 | Sylhet | 90 KM | 26 | 0% | NCC | Pending | Pending | 10th November 2016 | 6th | Done | Pending | Because of 23rd DNCC meeting, joint secretary halts our file till Oct 27, 2016.
10 | MBKULR-MBKUL2 | Sylhet | 90 KM | 15 | 75% | SCL | Done | Done | 42655 |  | Done | Pending
11 | PTAGR1-PTPNG1 | Patuakhali | 250KM | 8.569 | 100% | Hasan | Done | Done | 42622 |  | Done | Done
12 | PTPNG1-PTTWN1 | Patuakhali | 250KM | 9.168 | 100% | Hasan | Done | Done | 42622 |  | Done | Done
13 | PTTWN1-BRSKB2 | Patuakhali | 250KM | 6.611 | 100% | Hasan | Done | Done | 42622 |  | Done | Done
14 | PTAGR1-PTBRD1 | Patuakhali | 250KM | 9.312 | 100% | Hasan | Done | Done | 42622 |  | Done | Done
15 | PTBOG1-PTAMT1 | Patuakhali | 250KM | 19.883 | 100% | Hasan | Done | Done | 42622 |  | Done | Done
16 | BHCOS1-BHBKH1 | Bhola | 250KM | 6.314 | 100% | STL | Done | Done | 42487 |  | Done | Done
17 | CMELT2-BMBAN1-NGSON4 | Comilla | 250KM | 31.986 | 100% | SS | Done | Pending | 2016-11-10 | 4th | Done | pending | Additional chief engineer was not free due a meeting at Ministry
18 | SYBSN1-SNSAY1-MBSHE1 | Sylhet | 250KM | 15.592 | 100% | NCC | Done | Done | 42512 |  | Done | Done
19 | KSBZPR-KSKAT1 | Kishorgonj | 250KM | 14.783 | 100% | Btek | Done | Pending | 10th November 2016 | 6th | Done | pending | Because of 23rd DNCC meeting, joint secretary halts our file till Oct 27, 2016.
20 | NKDGP3-NKTWNR | Mymensing | 250KM | 25.674 | 100% | Shine | Done | Done | 42635 |  | Done | Done
21 | MGHCK1-MGDTA1 | Savar, Dhaka | 250KM | 8.452 | #REF! | STL | Done | Pending | 2016-11-10 | 2016-11-10 | pending | pending | CRA dept. asked to Mr. Mamun that if possible to take alternate route for this link. As per Mr. Mamun alternate route is not possible. CRA need arrange permission for the existing route. 3km permission done. Initial 30% pending due to Work request yet to be issue
22 | MYTWNR-MYBOU1-MYPRPR | Mymensing | 250KM | 0.6 |  | Shine | Pending (BR-GP) | Pending | Pending |  | pending | pending | GP depended. BD Railway permission needed. Initial 30% pending due to Work request yet to be issue
23 | MYPRPR-MYKAJ1-MYTWNR | Mymensing | 250KM | 1.522 | [6 empty] | pending | pending | Initial 30% pending due to Work request yet to be issue
24 | MYPRPR-MYCRP1-MYTWNR | Mymensing | 250KM | 2.283 | [6 empty] | pending | pending | Initial 30% pending due to Work request yet to be issue
25 | MDTWN5-MDCHLT-SPANG1 | Madaripur | 250KM | 10 |  | STL | Pending | Pending | Pending |  | pending | pending | SCL MD's concern and MOU with RHD.Initial 30% pending due to Work request yet to be issue
26 | GPJJR18 – GPSLN1 – GPJDPR1 | Gazipur | 250KM | 7.338 |  | Btek | Pending | Pending | Pending |  | pending | pending | BD Army permission issue. Initial 30% pending due to Work request yet to be issue
27 | NOHRT1-NOMJDT | Noawkhali | Regular | 17.364 | #REF! | SS | Done | Done | Pending |  | pending | pending
28 | MDTWN5-SPANG1 | Saridpur | 250KM | 14.386 | #REF! | Nijum | Pending | Pending | 2016-11-10 | 4th | pending | pending | SCL MD's approval needed. Initial 30% pending due to Work request yet to be issue
29 | SPANG1-SPBDG1 | Saridpur | 250KM | 15.128 | 83% | Hasan | Done | Pending | 10th November 2016 | 4th | pending | pending | Additional chief engineer was not free due a meeting at Ministry. Initial 30% pending due to Work request yet to be issue
30 | BSBOA1-BSBKG1 | Barisal | 250KM | 5.672 | #REF! | Hasan | 42666 | Pending | 2016-11-10 | 3dr | pending | pending | Additional chief engineer was not free due a meeting at Ministry. Initial 30% pending due to Work request yet to be issue
31 | BMAKAR-BMKUT3-CMMDBR | Comilla | 250KM | 9.857 | #REF! | SS | Done | Pending | 10th November 2016 | 6th | pending | pending | at Ministry. Initial 30% pending due to Work request yet to be issue
32 | GPMNA1-GPSRP1 | Gazipur | 250KM | 8.906 | 90% | Btek | Done | Pending | Pending | 0 | pending | pending | Vendor is asking for 190 tk/m, we don’t comply with that rate. Initial 30% pending due to Work request yet to be issue
33 | PGBDA1-NPBRG1 | Panchogor | 250km | 35 | 27% | Shine | Done | Pending | 2016-11-10 | 4th | pending | pending | Additional chief engineer was not free due a meeting at Ministry. Initial 30% pending due to Work request yet to be issue
34 | SRSJK2-JPTWNR | Mymensing | 250KM | 12.053 | 14% | Shine | Done | Done | 42659 |  | pending | pending
35 | JSCMK redundant fiber | Jessore | [10 empty] | Waiting for GP feedback
36 | CDTWNR-CDDMHT | Chaiganda | [10 empty] | Waiting for GP feedback