## Sheet1
Cross-functional Meeting between Admin & P&P
Date | 2016-10-27 |  | Time | 12:00-1:00 PM
Location | L2, NOC Meeting Room
Invitees | Ashok Kumar, Kowshik Mushfiq, Ashim Roy, Kazi Sifatul Kabir Shawon, Md. Kamal Uddin, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Sylhet Data Center window blocking issue | The windows of server room of Sylhet Data Center must be sealed. Admin team will take necessary steps sooner to resolve the matter. | Kazi Sifatul Kabir Shawon | 2016-11-25
|  | P&P concerned will confirm about what material can be used to seal window. | Kowshik Mushfiq | 2016-11-03
2 | Civil works activity completion at Polton PoP | Complete the civil works at Polton PoP at earliest | Kazi Sifatul Kabir Shawon, Md. Kamal Uddin | Open
4 | Sanction Load Upgradation | Sanction Load is required to be upgraded for the following sites: Bogra, Rajshahi, Tangail, Savar. Admin will take necessary steps to resolve the issue. | Md. Kamal Uddin | 2016-12-07