## leased line update
leased lines and requested capacity | Existing Lease Capacity | New Lease Capacity | Total Lease Capacity | Requirement placed to Marketing Team on | Feedback From Marketing | Update on 14th July 2016
Dinajpur-Rangpur | STM-1 | STM-3 | STM-4 | 2nd feb, 2016 | Possible | TDM interface is not possible for GP. However they have conveyed that the will discuss it with their management and provide a feedback by 25th July. Interim/alternate proposal from marketing team is to avail the links in IP/explore other operators such as BL/BTCL. Contact point for GP: Ripon Kumar Paul-8801711505762. Planning will convey if taking IP bandwidth will serve the purpose.
Rangpur to Lalmonirhat | STM-1 | STM-1 | STM-2 | 13th Jan, 2016 | Possible
Chapainawabganj To Rajshahi | STM-1 | STM-3 | STM-4 | 4th Jan, 2016 | Possible
Chapainawabganj To Naogaon | STM-1 | STM-3 | STM-4 | 13th Jan, 2016 | -
New Leased line requirement:
Area | Existing Lease Capacity | New Lease Capacity | Total Lease Capacity | Requirement placed to Marketing Team | Protection Status | Update on 14th July 2016
Bogra to Rajshahi | STM-5 | STM-3 | STM-8 | 19th April, 2016 | Unprotected | TDM interface is not possible for GP. However they have conveyed that the will discuss it with their management and provide a feedback by 25th July. Interim/alternate proposal from marketing team is to avail the links in IP/explore other operators such as BL/BTCL. Contact point for GP: Ripon Kumar Paul-8801711505762 Planning will convey if taking IP bandwidth will serve the purpose.
Dhaka to Sylhet | STM-4 | STM-10 | STM-14 | 19th April, 2016 | Unprotected
Dhaka to Bogra | STM-19 | STM-9 | STM-28 | 19th April, 2016 | Unprotected

## MOM
Location: Khansons Building, 4th floor meeting room
Attendees
Marketing: Iftekar Uddin, Sayed Rakib Ahmed, Ridwan Abdullah, Sayed khan, Farhadul Haque.
Planning: Sajia Sharmeen, Prianka Datta, Aushim Kumar Paul, Md. Shamsur Rahman.
S/N | Agenda | Discussion and Decision | Status | Timeline | Responsible
1 | Lease line Update (TDM capacity requirement) | GP has given feedback with pricing. SCl will place work order soon. | Open | 25/7/2016, | Marketing & GP
2 | Feasibility deletion option from marketing end | Marketing team will communicate with IT team to introduce the feasibility deletion option in TMS. Because some of the haulted feasibilitites remain in the TMS for days after days. | Open | - | Marketing
3 | Mentioning urgency of feasibility in TMS | Marketing team suggested that there should be an option during uploading feasibility which would depict whether the feasibility is urgent or not. Marketing team will communicate with IT team regarding this. | Open | - | Marketing
4 | Feasibility feedback with port unavailabity | Mention port unavailability at nearest pop during feasibility feedback | Open

## Sheet1
We need to share additional few more things with Marketing while providing feasibility. These are:
1. In case of dark core, we need to share Lat-Long of POC/EP.
2. In case of active link, we will mention route path.
For example-a link from Summit to Iswardi; We will provide necessary information with Route path. Route path-SCL own network/PGCB/Leased from operator etc
3. We will mention the operator name of sites in “Remarks” in TMS.
To Location | From Location | Remarks
Summit Center (Lat-Long) | Gaibandha POP (Lat-Long) | We will mention Gaibandha POP is GP/Robi/any other operator's site