## Sheet1
SL. | Link Name | Zone | Tag | Link Length (Km) | Total work Status | Vendor | Verbal Work Start Date | Permission Status | Permission Receive Date | Permission steps | Priority | Bill Status 30% | Bill Status 70% | Remarks
1 | MDSMD1-GGSTP1-FPBBR1 | Gopalgonj | 60 KM | 17.581 | 100% | SCL | Done | Done | Done |  |  | Done | Done
2 | BGDBL1-GGSTP1 | Gopalgonj | 60 KM | 33.658 | 100% | SS + MBCC | Done | Done | Done |  |  | Done | Done
3 | BSCOS1-BSBMHT-BSBOA2 | Barisal | 90 KM | 16.143 | 100% | SCL | Done | Done | Done |  |  | Done | Done
4 | NPBRG1 - NPTGM2 | Nilphamary | 90 KM | 31.142 | 100% | SCL | Done | Done | Done |  |  | Done | Done
5 | CGKTGT-HH | Chittagong | 90 KM | 1.65 | 100% | SCL | Done | Done | Done |  |  | Done | Pending | PAT done on 25 OCT,2016 including permission
6 | MNRMP1-MNMLK1 | Dhaka | CF | 7.4 | 100% | ABM | Done | Pending | Pending | 1st |  | Done | Pending | On Nov-2,2016 Vendor ABM will share the copy of demand note with SCL concern.. (Imp: until we complete "NGTWNR-MNRMP1". GP will not take hand over this link)
7 | NGTWNR-MNRMP1 | Dhaka | CF | 18.27 | 90% | ABM | Done | Pending | Pending | 1st |  | Done | Pending | SCL Management concern. (IMP:Muktarpur bridge permission issue (GP Concerned))
8 | MDSMD1-MDTWN5 | Madaripur | 60 KM | 11.135 | 10% | STL | Pending | Pending | Pending | 1st |  | Done | Pending | Pending for MOU.Without permission work cannot proceed (IMP:HDD stopped due to permission issue. Uncertain to complete by 2016)
9 | SNJAW1-SNMOL1 | Sylhet | 90 KM | 26 | 0% | NCC | Pending | Done | Done | 6th |  | Done | Pending | To start HDD need permission of RHD. LGED permission done only 500m
10 | MBKULR-MBKUL2 | Sylhet | 90 KM | 15 | 75% | SCL | Done | Done | 42655 |  |  | Done | Pending | (Imp:HDD started from 12 Oct,2016.)
11 | PTAGR1-PTPNG1 | Patuakhali | 250KM | 8.569 | 100% | Hasan | Done | Done | 42622 |  |  | Done | Done
12 | PTPNG1-PTTWN1 | Patuakhali | 250KM | 9.168 | 100% | Hasan | Done | Done | 42622 |  |  | Done | Done
13 | PTTWN1-BRSKB2 | Patuakhali | 250KM | 6.611 | 100% | Hasan | Done | Done | 42622 |  |  | Done | Done
14 | PTAGR1-PTBRD1 | Patuakhali | 250KM | 9.312 | 100% | Hasan | Done | Done | 42622 |  |  | Done | Done
15 | PTBOG1-PTAMT1 | Patuakhali | 250KM | 19.883 | 100% | Hasan | Done | Done | 42622 |  |  | Done | Done
16 | BHCOS1-BHBKH1 | Bhola | 250KM | 6.314 | 100% | STL | Done | Done | 42487 |  |  | Done | Done
17 | CMELT2-BMBAN1-NGSON4 | Comilla | 250KM | 31.986 | 100% | SS | Done | WIP | 2016-11-10 | 4th | 1 | Done | pending | Additional chief engineer was not free due a meeting at Ministry. Permission received only for B.Baria Zila porisod 14Km.PAT is ongoing
18 | SYBSN1-SNSAY1-MBSHE1 | Sylhet | 250KM | 15.592 | 100% | NCC | Done | Done | 42512 |  |  | Done | Done
19 | KSBZPR-KSKAT1 | Kishorgonj | 250KM | 14.783 | 100% | Btek | Done | Done | Done | 6th |  | Done | pending
20 | NKDGP3-NKTWNR | Mymensing | 250KM | 25.674 | 100% | Shine | Done | Done | 42635 |  |  | Done | Done
21 | MGHCK1-MGDTA1 | Savar, Dhaka | 250KM | 8.452 | 80% | STL | Done | WIP | 2016-11-10 | 2016-11-10 | 1 | pending | pending | Survey is ongoing. Alternate route is not possible. CRA need arrange permission for the existing route. 3km permission done. Initial 30% pending due to Work request yet to be issue. (IMP: Work stoped due to permission in opposite side of road, poroshova done 3Km.)
22 | MYTWNR-MYBOU1-MYPRPR | Mymensing | 250KM | 0.6 | 0% | Shine | Pending (BR-GP) | Pending | Pending |  |  | pending | pending | GP concern will sign drawing on Nov-01-2016.GP depended. BD Railway permission needed. Initial 30% pending due to Work request yet to be issue
23 | MYPRPR-MYKAJ1-MYTWNR | Mymensing | 250KM | 1.522 | [7 empty] | pending | pending | Initial 30% pending due to Work request yet to be issue
24 | MYPRPR-MYCRP1-MYTWNR | Mymensing | 250KM | 2.283 | [7 empty] | pending | pending | Initial 30% pending due to Work request yet to be issue
25 | MDTWN5-MDCHLT-SPANG1 | Madaripur | 250KM | 10 | 0% | STL | Pending | Pending | Pending |  |  | pending | pending | SCL Management concern and MOU with RHD.(IMP:Waiting for permission to start HDD & Depand on SL 15). Initial 30% pending due to Work request yet to be issue
26 | GPJJR18 – GPSLN1 – GPJDPR1 | Gazipur | 250KM | 7.338 | 0% | Btek | Pending | Pending | Pending |  | 2 | pending | pending | GP will resurvey this link on Nov-02-2016.BD Army permission issue. Initial 30% pending due to Work request yet to be issue
27 | NOHRT1-NOMJDT | Noawkhali | Regular | 17.364 | 75% | SS | Done | Done | Pending |  |  | pending | pending | LGED permission done, RHD pending
28 | MDTWN5-SPANG1 | Saridpur | 250KM | 14.386 | 52% | Nijum | Pending | Pending | 2016-11-10 | 4th | 3 | pending | pending | SCL Management s approval needed. Mou.Initial 30% pending due to Work request yet to be issue
29 | SPANG1-SPBDG1 | Saridpur | 250KM | 15.128 | 83% | Hasan | Done | WIP | 10th November 2016 | 5th | 1 | pending | pending | Additional chief engineer was not free due a meeting at Ministry. (IMP:Permission done for zila porishod done7.500Km, RHD pending)Initial 30% pending due to Work request yet to be issue
30 | BSBOA1-BSBKG1 | Barisal | 250KM | 5.672 | 70% | Hasan | 42666 | WIP | 2016-11-10 | 3dr | 1 | pending | pending | Additional chief engineer was not free due a meeting at Ministry. Initial 30% pending due to Work request yet to be issue
31 | BMAKAR-BMKUT3-CMMDBR | Comilla | 250KM | 9.857 | 38% | SS | Done | WIP | 10th November 2016 | 6th | 1 | pending | pending | at Ministry. (IMP: 2.7Km HDD done with verbal permission) Initial 30% pending due to Work request yet to be issue
32 | GPMNA1-GPSRP1 | Gazipur | 250KM | 8.906 | 93% | Btek | Done | Pending | Pending | 0 | 1 | pending | pending | Vendor is asking for 190 tk/m, we don’t comply with that rate. Initial 30% pending due to Work request yet to be issue.Pending for MOU
33 | PGBDA1-NPBRG1 | Panchogor | 250km | 35 | 53% | Shine | Done | WIP | 2016-11-10 | 5th | 3 | pending | pending | chief engineer was not free due a meeting at Ministry. Initial 30% pending due to Work request yet to be issue
34 | SRSJK2-JPTWNR | Mymensing | 250KM | 12.053 | 75% | Shine | Done | Done | 42659 |  |  | pending | pending
35 | JSCMK redundant fiber | Jessore |  | 6km | 0% |  |  | WIP | Pending |  |  |  |  | Waiting for GP feedback
36 | CDTWNR-CDDMHT | Chaiganda | [11 empty] | Waiting for GP feedback

## Sheet3
SL. | Link Name | Zone | Total work Status | Vendor | Permission Receive Date | Bill Status 30% | Bill Status 70%
6 | MNRMP1-MNMLK1 | Dhaka | 100% | ABM | Pending | Done | Pending
7 | NGTWNR-MNRMP1 | Dhaka | 90% | ABM | Pending | Done | Pending
8 | MDSMD1-MDTWN5 | Madaripur | 10% | STL | Pending | Done | Pending
9 | SNJAW1-SNMOL1 | Sylhet | 0% | NCC | 10th November 2016 | Done | Pending
17 | CMELT2-BMBAN1-NGSON4 | Comilla | 100% | SS | 2016-11-10 | Done | pending
19 | KSBZPR-KSKAT1 | Kishorgonj | 100% | Btek | 10th November 2016 | Done | pending
21 | MGHCK1-MGDTA1 | Savar, Dhaka | 80% | STL | 2016-11-10 | pending | pending
22 | MYTWNR-MYBOU1-MYPRPR | Mymensing | 0% | Shine | Pending | pending | pending
25 | MDTWN5-MDCHLT-SPANG1 | Madaripur | 0% | STL | Pending | pending | pending
26 | GPJJR18 – GPSLN1 – GPJDPR1 | Gazipur | 0% | Btek | Pending | pending | pending
28 | MDTWN5-SPANG1 | Saridpur | 52% | Nijum | 2016-11-10 | pending | pending
29 | SPANG1-SPBDG1 | Saridpur | 83% | Hasan | 10th November 2016 | pending | pending
30 | BSBOA1-BSBKG1 | Barisal | 70% | Hasan | 2016-11-10 | pending | pending
31 | BMAKAR-BMKUT3-CMMDBR | Comilla | 31% | SS | 10th November 2016 | pending | pending
32 | GPMNA1-GPSRP1 | Gazipur | 93% | Btek | Pending | pending | pending
33 | PGBDA1-NPBRG1 | Panchogor | 45% | Shine | 2016-11-10 | pending | pending