## Sheet1
Cross-functional Meeting between Gateway & P&P
Date | 2016-11-01 |  | Time | 11:00 AM-12:00 PM
Location | L2, Outer Meeting Room
Invitees | Samiul Bashar, Shahidullah Kaiser, Kowshik Mushfiqur Rahman, Ashok Kumar, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Google Server Dismantle | Google server is required to be dismantled from Dhaka Data Center. | Samiul Bashar | 2016-11-15
2 | Future load requirement and device installation forecast | IIG team will share a forecast for their near future load requirement and required probable device installation timelines. | Samiul Bashar | 2016-11-08
3 | Load Shifting to Polton PoP | IIG will shift their loads to Polton pop from Dhata Data Center. According to their plan the distribution switches will remain where they exist. Routers and servers will be shifted to Polton PoP. | Samiul Bashar, Kowshik Mushfiq, Ashok Kumar | Open
4 | Load forecast for Dhaka Data Center and Polton PoP | IIG shared a load forecast for Dhaka Data Center and Polton pop. P&P Concern will check the feasability and provide necessary update within given timeline. | Kowshik Mushfiq | 2016-11-04
5 | Benapole PoP Shifting | The device shifting plan of Benapole pop is postponed to November 15th due to dependency on supply end. The device has not been available yet to install. | Shahidullah Kaiser | 2016-11-15
6 | Uttora PoP Load forecast | IIG team provided a load forecast of 3.5 KW requirement to install 3 servers and 1 switch at Uttara PoP. P&P concern will check the feasability and provide update. | Kowshik Mushfiq | 2016-11-04