## MOM
Date | 2016-11-02 |  |  |  | Time |  | 11:30 am-12:30 pm
Location | Khansons Building Level 5 Meeting room
Meeting Title | Weekly meeting between O&M and Planning Team
Agenda | Follow up and Catch up on various tasks
| OM-1 & OM-2 |  |  | Nazmul Huda Sumon
Attendees |  |  |  | Sarjana Jahan
Shamama Shahrin Arani
Musabbir Chowdhury
Touhid Al Imran
Md. Mustafezur Rahman
Abdullah Md Saleh
| PAD |  |  | Afjal Hossain Khan
Nuruzzaman Rasel
Juhi Johana Bashir
Sl | Discussion Point | Discussion / Decision |  |  |  | Responsible |  | Deadline | Status | Remarks
| Location level redundancy at Pubail, Vulta. | Location level redundancy achieved for 2GEs under DRE01; scheduled activity for "Location level redundancy for Pubail" has been re-scheduled by Robi due to Robi's network freezing. Revised schedule is yet to be shared by Robi. |  |  |  | PAD ,O&M, Khairul, Imran & Nazmul |  | - | Open | Pending 6GE shifting schedule to be provided by ROBI. PAD has already communicated regarding the schedule.Robi has provided shedule. OM team communicated with Robi regarding NCR and shifting activity.
1
2 | Dhaka region ROBI & GP third path Dhaka region(GP Third path and Robi Third Path) | GP third path | The required activities for third path configuration are: 1. Configuration of flood group for ISIS will be done. For this required Junos version will be shared by juniper 2. Flood group will be configured at test bed(responsibel:PAD & juniper) 3. after successful floodgroup testing we will start adding third path (responsible: PAD & juniper). 4. juniper will verify the third path configuration testing and based on juniper configuration we will deploy our network. |  |  | O&M, PAD, Ronjue, Imran,Nazmul |  | _ | Open | Testing done. Test result is not satisfactory. We have shared test result with Juniper. Juniper Engineer will travel Bangladesh and will work with us to achieve our desired out put. Imran and Nazmul bhai will communicate with Ronjue bhai.
|  | Robi third path |  |  |  | O&M, PAD, Ronjue, Imran,Nazmul |  | _ | Open
3 | FTTB UPDATE | FTTB project team will provide update to planning on regular basis |  |  |  | FTTB team, Afzal & Azam |  | - | ongoing | Rest of the pending links will be provided to PAD.FTTB team provided cable blowing update(gulshan shooting club to gul-2) to PAD according to provided plan.new cable blowing.
4 | Shahabagh-Jalkhabar cable chanage | 96 cable dismantel and shift to 432 cable |  |  |  | PAD & Redden, Arafat,Arani & Afjal |  | Planning will provide plan for 5 links in every sunday and redden execute will all the links in that week. | ongoing | work in progress
5 | Link dismantle | Redden team will execute pending UG core dismantle backlog plan of client provided by PAD |  |  |  | Redden, Arafat & Ujjal |  | 20/10/2016,26/10/2016 | closed
7 | Pending Feedback and Core Change | OM team will response with the pending feedback and Core change issues . |  |  |  | OM, Arafat,Arani & Ujjal |  |  | ongoing | Operation team will provide update to PAD for every change.
8 | Narsingdi to kisorgonj redundant backbone | Need to build new messanger path from NS2302 to KS1858 to protect Narsingdi Traffic |  |  |  | OM-1, Samiul & Rezaul Karim |  | 15/10/2016,15/11/2016,10/12/2016 | Open | Total distance is 30km. Fiber pulling for 20km will be done by the deadline.Pole issue for the rest 10km .
9 | GP ring modification | PAD is working on this issue and separate discussion is needed with both operation team based on this requirement |  |  |  | PAD, Sajia & Sunve |  | - | Ongoing | PAD will provide plan as per discussion.
10 | Ashugonj to Al hamra redundent link | Need to build this link for traffic protection for Sylhet region |  |  |  | Arani |  | 30/10/2016 | closed | 23km done out of 30km
11 | Bogra-Rangpur-Dinajpur BB link | Need to build this BB link through north_Zone traffic protection |  |  |  | Piash |  | 20/11/2016 | Open
12 | Remaining PGCB link light-up | To protect existing traffic through PGCB |  |  |  | Prianka, Musabbir & Anup |  | 20/11/2016 | Open | Device plan will be provided after fiber light up plan from pgcb project team.
13 | Device swapping: ACX-1000 with ACX-1100 | Got 60 nos from OM-2 and 40 from OM-1. OM will give update by today about rest of the devices |  |  |  | Rezaul & Proshanta |  | 26/10/2016, 2/12/2016 | open | weekly 25 device will be Handed over to PAD by OM team.
14 | sylhet regional HO for Robi | Planning team will communicate with Robi and provide update to OM team. |  |  |  | Khairul Alam |  | ; | open