## Sheet1
Cross-functional meeting between IT & P&P
Date | 2016-11-06 |  | Time | 3:00 PM- 4:00 PM
Location | L5, Khansons Meeting room
Invitees | Ziaul Haque, Pranabesh Mozumder, Toufiq Zaman, Kowshik Mushfiqur Rahman, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | T.K Bhaban UPS Installation Issue | AC power would be provided to T.K. Bhaban UPS by P&P team according to the plan provided by IT team. | Kowshik Mushfiqur Rahman, Ziaul Haque | 2016-11-20
2 | Update List of sites with Generator | An updated site list will be provided to IT involving sites which have generators installed. | Toufiq Zaman | 2016-11-18
3 | CCTV Camera installation at Backbone sites | IT team will install CCTV camera to the remaining Backbone sites. The site list will be provided by P&P team | Toufiq Zaman, Kowshik Mushfiqur Rahman | 2016-11-18
4 | Admin Access to PoP & Power Room of all sites | A list of names will be provided to IT team for giving admin access to respective zonal concern from P&P team. IT team will ensure providing the access to individuals | Ziaul Haque, Pranabesh Mozumder,Kowshik Mushfiqur Rahman | 2016-11-18
5 | UPS connection to Printer | P&P team will check the feasibility of providing UPS connection to printer | Kowshik Mushfiqur Rahman | Open