## MOM
Date | 2016-11-13 |  |  |  | Time |  | 11:30 am-12:30 pm
Location | Khansons Building Level 5 Meeting room
Meeting Title | Weekly meeting between O&M and Planning Team
Agenda | Follow up and Catch up on various tasks
| OM-1 & OM-2 |  |  | Nazmul Huda Sumon
Attendees |  |  |  | Sarjana Jahan
Shamama Shahrin Arani
Musabbir Chowdhury
Touhid Al Imran
Md. Mustafezur Rahman
Abdullah Md Saleh
| PAD |  |  | Afjal Hossain Khan
Nuruzzaman Rasel
Juhi Johana Bashir
Sl | Discussion Point | Discussion / Decision |  |  |  | Responsible |  | Deadline | Status | Remarks
| Location level redundancy at Pubail, Vulta. | Location level redundancy achieved for 2GEs under DRE01; scheduled activity for "Location level redundancy for Pubail" has been re-scheduled by Robi due to Robi's network freezing. Revised schedule is yet to be shared by Robi. |  |  |  | PAD ,O&M, Khairul, Imran & Nazmul |  | - | Open | Pending 6GE shifting schedule to be provided by ROBI. PAD has already communicated regarding the schedule.Robi has provided shedule. OM team communicated with Robi regarding NCR and shifting activity.
1
2 | Dhaka region ROBI & GP third path Dhaka region(GP Third path and Robi Third Path) | GP third path | The required activities for third path configuration are: 1. Configuration of flood group for ISIS will be done. For this required Junos version will be shared by juniper 2. Flood group will be configured at test bed(responsibel:PAD & juniper) 3. after successful floodgroup testing we will start adding third path (responsible: PAD & juniper). 4. juniper will verify the third path configuration testing and based on juniper configuration we will deploy our network. |  |  | O&M, PAD, Ronjue, Imran,Nazmul |  | _ | Open | . Imran and Nazmul bhai will communicate with Ronjue bhai by today and provide feedback after testing
|  | Robi third path |  |  |  | O&M, PAD, Ronjue, Imran,Nazmul |  | _ | Open
3 | FTTB UPDATE | FTTB project team will provide update to planning on regular basis |  |  |  | FTTB team, Afzal & Azam |  | - | ongoing | Rest of the pending links will be provided to PAD.FTTB team provided cable blowing update(gulshan shooting club to gul-2) to PAD according to provided plan.
4 | Shahabagh-Jalkhabar cable chanage | 96 cable dismantel and shift to 432 cable |  |  |  | PAD & Redden, Arafat,Arani & Afjal |  | Planning will provide plan for 5 links in every sunday and redden execute will all the links in that week. | ongoing | work in progress
5 | Link dismantle | Redden team will execute pending UG core dismantle backlog plan of client provided by PAD |  |  |  | Redden, Arafat & Ujjal |  | 20/10/2016,26/10/2016 | closed
7 | Pending Feedback and Core Change | OM team will response with the pending feedback and Core change issues . |  |  |  | OM, Arafat,Arani & Ujjal |  |  | ongoing | Operation team will provide update to PAD for every change.
8 | Narsingdi to kisorgonj redundant backbone | Need to build new messanger path from NS2302 to KS1858 to protect Narsingdi Traffic |  |  |  | OM-1, Samiul & Rezaul Karim |  | 15/10/2016,15/12/2016 | Open | Total distance is 30km. Fiber pulling for 20km will be done by the deadline.Pole issue for the rest 10km .
9 | GP ring modification | PAD is working on this issue and separate discussion is needed with both operation team based on this requirement. Om will share a priority ring list according to which modification has to be done. |  |  |  | PAD, Sajia & Sunve |  | - | Ongoing | PAD will provide plan as per discussion. Third path test trial will be implemented this week. Upon successful result plan will be provided accordingly.
10 | Ashugonj to Al hamra redundent link | Need to build this link for traffic protection for Sylhet region |  |  |  | Arani |  | 30/10/2016 | closed | 23km done out of 30km
11 | Bogra-Rangpur-Dinajpur BB link | Need to build this BB link through north_Zone traffic protection |  |  |  | Piash |  | 20/11/2016 | Open
12 | Remaining PGCB link light-up | To protect existing traffic through PGCB |  |  |  | Prianka, Musabbir & Anup |  | 20/11/2016 | Open | Device plan will be provided after fiber light up plan from pgcb project team.
13 | Device swapping: ACX-1000 with ACX-1100 | Got 60 nos from OM-2 and 40 from OM-1. OM will give update by today about rest of the devices |  |  |  | Rezaul & Proshanta |  | 26/10/2016 | closed | weekly 25 device will be Handed over to PAD by OM team.
14 | sylhet regional HO for Robi | Planning team will communicate with Robi and provide update to OM team. |  |  |  | Khairul Alam |  |  | open