## 23.10.2016
Date | 2016-11-13
Location | Khan Sons
Meeting Title | Regular Weekly meeting between Implementation and Planning Team
Agenda | Follow up and Catch up on various tasks
Attendees | Implementation |  | A.K.M Mahmud Hossain
Mohammad Rizwanul Islam
Obaidullah Al Masum
Md. Abdullah Al Mamun
Ehsan Karim
Arafat Islam
Ibrahim Sharif
Arun Kumar Roy
Naushin Reza
Naieem Mahmood Nitul
Md. Shamsuzzaman
Tofazzol Hossain
Uttom Sharma
Sharif Abul Kalam Azad
| Planning |  | Afjal Hossain Khan
Nuruzzaman Rasel
Juhi Johana Bashir
Md.Bakul Miah
SL No. | Discussion Point | Discussion/Decision | Responsible | Deadline | Status | Remarks
1 | Cable Blowing from Jahangir gate to Proshanti POC | Permission from cantonment board is yet to get. Work will be commenced by respective department after getting permission. | Implementation (Civil & UG) | 8/31/2015, 9/14/2015 10/5/2015 10/19/2015 11/9/2015 12/7/2015, 3/15/16 (no deadline can be set until we get permission) | closed | According to the permission letter that civil team received from cantonment board, All NTTNs have to work at the same time.Therefore permission letter need to revise as per civil team feedback.Corporate Affairs working to get new permission. Alternative solution: Core rearrangement to get free core. Core rearrangement and red limpia both can be performed under same permission. This issue has been escalated to higher management by Ehsan Bhai and subsecuently to cantonment board. Waiting for final feedback from cantonment board. Ehsan Bhai will share the follow up mail communications. This issue has been persued through technical admin. No feedback of permission acquired.
2 | GP old 100 sites update | Implementation team will share the work status of GP first 100 sites. The project is ongoing. | Implementation(Naieem Mahmood) | Weekly update | Open | As per last update from I&C team, OH done for 97 sites, vertical done 91 sites, Device deployed in 92 sites and 89 sites incorporated in network and service provisioning done for 76 sites, GP issue 10 sites. PAT done for 61 sites.
3 | UG Network deployment status | UG Network deployment status needs to be updated by UG team within Thursday of every week. Updated file will be provided by UG team. | Implementation (UG & Civil)(Uttom Sharma) | Weekly update | Ongoing | Uttom bhai
4 | Bi-weekly UG KMZ and coverage update | UG team will provide KMZ of newly deployed UG network along with Bi-weekly update. UG team will provide the bi-weekly update according to the new format which will be shared by planning team. | Implementation(UG)(Uttom Sharma) | Bi-weekly update | Ongoing | Uttom Bhai.
5 | Update from IMP team for all links as per provided work plan from PAD | PAD will share the provided work plan list weekly with IMP team and IMP team will provide update accordingly. | PAD & IMP(Mohebubur Rahman) | Weekly update | Ongoing | After receiveing any kind of work plan from PAD regarding handover links, IMP team will provide update as per recommended timeline. Also Number of T-joint will be shared with Plan.
7 | IPLC underground readiness Status | 3 out of 15 are completed | IMP (CIVIL UG) | 15/11/2016 | Open | civil work has done for 3 links.The rest is pending due to permission issue. IMP team will provide timeline for whole task after getting permission from corporate affairs. Civil team communicated with corporate affairs via mail. Got permission for 1 more link. Timeline for that link is 15th November,2016 . permission pending for rest 11 links. As per corporate affairs feedback we may get permission within next week for rest of the links.
8 | T-joint update after each plan mismatch | Implementation team will provide update for each plan mismatch | IMP( Sharif Abdul Kalam Azad) | - | On going | -
9 | Timeline required for UG Phase-1,Phase-2 & Phase-3 | UG civil team will Share specific timeline for all links from the existing approval. | IMP (CIVIL UG) | - | Ongoing | IMP team will provide timeline by 27/09/2016 for the whole task. Due to approval issue IMP team could not provide timeline. This issue has been escalated to Mahmud Sir. Got permission for 3 links of phase-2 and 14 of phase-3.
11 | Network expansion and modification | Implementation civil team will start working in 10 days after getting permission. 7 days are required for tjoint splicing. | IMP (CIVIL UG) & client | - | closed | Implementation team aligned with this timeline
12 | Ashugonj to Sylhet Link via messenger | To build redundant BB link for Dhaka_Sylhet | IMP(OH) Ibrahim Sharif | 10/11/2016, 25/11/16 | Open | 34km done out of 55 km.
13 | BOG-RANG-DINAJ rearrangement via messenger | To build redundant BB link for North zone | IMP(OH) Ibrahim Sharif | 2016-05-12 | open | 60km done out of 121km.
14 | Motijheel FTTB update | Implementation civil team will give update about Motijheel FTTB existing status. | IMP (CIVIL UG) | - | open | management approval done. permission pending at corporate affairs
15 | Gopalgonj-Madaripur-Takerhut | Need to deploye UG cable for Goplagonj to Madaripur protection | IMP ( Civil UG ) | 20/11/2016 | open