## Sheet1
Cross-Functional Meeting - NOC and P&P
Date | 2016-07-20 |  | Time | 3:40 PM - 4:20 PM
Location | L5 - Meeting Room, Khan Sons Building
Invitees | Mir Raihan Md Maeen, Raihan Parvez, Rajibul Islam, Md. Shariful Islam, Md. Rubel Khan, S.M Mubasser Hossain, A. H. M Rowfut Tafsiri, Kowshik Mushfiqur Rahman, Ashok Kumar Biswas, Umana Rafiq |  | Attendees | Rajibul Islam, Sakib Ullah, S.M Mubasser Hossain, A. H. M Rowfut Tafsiri, Umana Rafiq
Sl. No. | Agenda |  | Responsible |  | Timeline | Remarks
1 | IP-based Alarm Monitoring Process | NOC will start monitoring and circulating the IP-based alarm. P&P team has already shared an updated IP list and IP-based Alarm Monitoring Process for this purpose | Rajibul Islam, Sakib Ullah (NOC) |  | Open | Will provide an update within a short period of time
2 | ZTE Alarm Notification | NOC will set the standard alarm notification time for ZTE alarm monitoring to 1-2 hours in order to avoid further alarm notification delay that has been occuring recently. | Rajibul Islam, Sakib Ullah (NOC) |  | Immediate Action
3 | Regarding Alarm Dashboard | P&P team will provide a list of names who will be responsible for notifying or commenting for clearing the dashboard | Kowshik Mushfiqur Rahman (P&P) |  | Open
4 | Alarm Notification SLA | NOC will provide alarm notification through SMS followed by an immediate phone call after office hours (11:00 PM to 8:00 AM) to individuals according to the provided escalation matrix. | Rajibul Islam, Sakib Ullah (NOC) |  | Open