## Sheet1
Departmental Weekly Meeting
Date | 2016-07-22 |  | Time | 10:30m-1:00PM
Location | L5, Meeting Room, Khan Sons Building
Invitees | Md. Musleh Uddin, Md. Rubel Khan, S. M. Mubasser Hossain, Kowshik Mushfiq-Ur-Rahman, Ashok Kumar Biswas, M. Alimuzaman, Rowfut Tafsiri, Toufiq Zaman, Tousif Zaman, Umana Rafiq |  | Attendees | Md. Musleh Uddin, S. M. Mubasser Hossain, Kowshik Mushfiq-Ur-Rahman, Ashok Kumar Biswas, M. Alimuzaman, Rowfut Tafsiri, Toufiq Zaman, Tousif Zaman, Umana Rafiq
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Fault Handling based on criticality | Analyze the criticallity for all SCL nodes and create a report providing fault observation time immediately after which an engineer should reach the site and handle the fault. Prepare and circulate SLA according to the analysis. | Rowfut Tafsiri | Open
2 | Marking of Fixed Assets | Mark the fixed assets across all zones accordingly. Specify incoming and outgoing point as well while marking. | Rowfut Tafsiri | 2016-08-15
3 | Fluke Power Analyzer | Analyze the specification and usage for Fluke Power Analyzer | Rowfut Tafsiri | 2016-07-29
4 | Departmental Expenditure Calculation | Calculate the total departmental expenditure from the month of January to June including - PO (capex & opex), Tour Bills, Vehicle Cost, Salary, Fuel Cost and other expenditure and prepare an analysis report for the same. | Toufiq Zaman | 2016-08-05
5 | Standard Working Procedure | Merge all Operational activity standards with the existing Standard Working Procedures for automation purpose | S. M. Mubasser Hossain | Open