## Sheet1
Cross-Functional Meeting between O&M (PGCB) and P&P
Date | 2016-07-21 |  | Time | 3:00PM - 4:00PM
Location | L2, NOC Meeting Room, Khan Sons Building
Invitees | Md. Ahsanur Rab, Abdullah Saleh, Mahmud Hossain, Mizanul Islam, Md. Musleh Uddin, S. M. Mubasser Hossain, Ashok Kumar Biswas, Md. Rubel Khan, Sayda Kamrun Jahan Ripa. |  | Attendees | Mizanul Islam, Sayda Kamrun Jahan Ripa, S. M. Mubasser Hossain, Ashok Kumar Biswas
Sl. No. | Agenda | Description | Responsible |  | Timeline | Remarks
1 | Regarding PGCB space expansion issue | In order to design a standard power system comparing the existing load status and load forecast we require the space of PGCB to be expanded. O&M PGCB team has already made an agreement with PGCB. P&P team will provide their requirement with timeline. | Ashok Kumar (P&P) |  | Open
3 | Regarding PGCB accessed by Vendors | Vendors must access to any PGCB with an SCL representative accompanying them. | Minhazul Islam (O&M-PGCB) |  | Immediate action
3 | DWDM expansion forecast | PGCB team will provide forecast in the next meeting regarding any new equipment installation | Minhazul Islam (O&M-PGCB) |  | 2016-08-04