## Sheet1
Date | 2016-12-30 | Time | 10:30 AM-12:00 PM
Location | Sadman Tower(4th Floor),Dhamsona, Dandabor, Ashulia-Savar
Meeting Title | Weekly meeting between SCL operation team and vendor Ideal Cable TV Network for O&M issues
Participants | Fakhrul Alam Majumder,Md.Rasel,Rakibul Hassan,Md.Abu Bakkar Siddik
Md.Abdur Rahman,Md.Riadh .,Md.Akhteruzzaman,Md.Bablu
Agenda | Agenda Discussion |  | Responsible | Deadline | Status | Remarks
link share found .Need adjust from WCC | DHDHM10 to MGSDR01 & DHDHM10 to Info-sarker Saturia Upozilla SW-1 link cable sharing found (20.498 KM) but in WCC both link is separate.Need adjust from WCC |  | SCL team | 2017-01-07 | Open
Cash Transaction | All kind of cash txn will be totally prohibited with any Info-Client or offices. |  | SCL & Ideal team | Continue | Open
LD Report Settlement | Monthly link down tracker need to submit for LD settlement issue |  | Ideal team | 2016-12-30 | Open
PM Report(Info-Sarker) | PM report need to submit .Already sample shared by SCL team |  | Ideal team | 2017-01-02 | Open
Info-Sarker Link down issue | Info-Sarker every link down SMS notification will be send by SCL on-call concern(zonal) |  | SCL team | 2017-01-07 | Open
Info-Sarker PM issue | During info-Sarker PM work,need info like cable ID & start to end meter reading.Also marking the TJ as instructed. |  | Ideal Team | Continue | Open
Link Down Issue | Before move to All kind of link down issue should take decision from SCL on-call concern |  | Ideal Team | Continue | Open