## Sheet1
Meeting Minutes
Date | 2017-01-16 |  | Time | 4:30 PM – 5:30 PM
Location | L-5 Meeting Room, Khan Sons Building.
Attendees | Abdul Jabbar Kbir, S.M. Arifunul Karim, Kazi Sifatul Kabir Shawon, Zisan Zaman, Md. Rubel Khan, Ashok Kumar Biswas, Sabrina Amin
Sl. No. | Agenda | Description | Responsible |  | Timeline | Remarks
1 | Required load accomodation in Banani DR | As there are space and genset issue present at the moment in Banani DR P&P concerns are unable to provide required load (6 KW), these issues will be raised and discussed in HoD meeting and share a recovary plan. | Abdul Jabbar Kabir |  | 2017-01-18
2 | Power availability in Paltan PoP | New power setup at Paltan PoP is ready and required device can be powered up at any time. Planning team will share the specific installation date with P&P concern. | S.M. Arifunul Karim |  | Open
3 | Space allocation in Uttara PoP | P&P team will share the proposed space extension which is needed to be extended to accommodate new power system with PoP project team. | Md. Rubel Khan |  | 2017-01-18
4 | Genset space and sanction load up gradation at Uttara PoP | Admin team will contact with the building authority of Uttara PoP regarding the permission and required space for genset installation along with up gradation of existing sanction load. | Kazi Sifatul Kabir Shawon |  | 2017-01-17
5 | Shifting of MX-480 in Dhanmondi PoP | New MX-480 at Dhanmondi PoP will be installed in the existing rack and traffic from old device will be shifted to new MX-480 and planning team will share the specific sheduled date with P&P. | S.M. Arifunul Karim |  | Open
|  | This MX-480 shifting in Dhanmondi PoP will take 6 hrs and in the mean time P&P will provide PG support incase of any emergency. | Md. Rubel Khan |  | Open
6 | New office location for Dhanmondi PoP | Planning team will complete the survey for new office location for Dhanmondi PoP | S.M. Arifunul Karim |  | Open
7 | Installation schedule of 10G up gradation for Robi | Planning team will share the installation schedule of Huawei OptiX OSN1800 | S.M. Arifunul Karim |  | Open
|  | P&P team will ensure required power for the installation of Huawei OptiX OSN1800 in specific nodes. | Md. Rubel Khan |  | Open
8 | Banani, Mirpur, Uttara | Civil works / new site readyness / expansion of Banani, Mirpur, Uttara will be completed within 15th March, 2017 | Abdul Jabbar Kabir |  | 2017-03-15