## Sheet1
SI. No. | Site Name | Description | Responsible | Timeline
1 | Comilla_A | Site finalization will be done by 13-Jan-17. | Md. Adbul Jabbar Kabir (OM-2) | 13-Jan-17
|  | Commercial Power Connection of the site will be given by 1-Feb-17. | Md. Rezaul Haque (SCM) | 2017-02-01
2 | Choddogram_A | Design will be shared by Md. Abdul Jabbar with P&P team. | Md. Adbul Jabbar Kabir (OM-2) | 2016-01-12
|  | PoP readyness date will be 1-Feb-16. | Md. Adbul Jabbar Kabir (OM-2) | 2016-02-01
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
3 | Sitakundo_A | Design will be shared by Md. Abdul Jabbar with P&P team. | Md. Adbul Jabbar Kabir (OM-2) | 2016-01-12
|  | PoP readyness date will be 1-Feb-16. | Md. Adbul Jabbar Kabir (OM-2) | 2016-02-01
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
4 | Satkania_A | PoP readyness date will be 1-Feb-16. | Md. Adbul Jabbar Kabir (OM-2) | 2016-02-01
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
5 | Chokoria_A | PoP readyness date will be 1-Feb-16. | Md. Rezaul Haque (SCM) | 2016-02-01
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
6 | Cox's Bazar_A | PoP readyness date will be 15-Feb-16 | Md. Adbul Jabbar Kabir (OM-2) | 2016-02-15
|  | Power readyness date will be 17-Feb-16 | Md. Rubel Khan | 2016-02-17
|  | UG readyness date will be 24-Feb-16 | AKM Mahmud Hossain | 2016-02-24
7 | Sonargaon_P | Commercial Power connection will be given by 11-Feb-16 | Md. Rezaul Haque (SCM) | 2016-02-11
|  | PoP readyness date will be 1-Feb-16. | Md. Adbul Jabbar Kabir (OM-2) | 1-Feb-16.
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
8 | Daudkandi_P | Commercial Power connection will be given by 11-Feb-16 | Md. Rezaul Haque (SCM) | 2016-02-11
|  | PoP readyness date will be 1-Feb-16. | Md. Adbul Jabbar Kabir (OM-2) | 1-Feb-16.
|  | PO will be issued on 11-Jan-16 | Md. Rezaul Haque (SCM) | 2016-01-11
9 | Feni_P | Drawing will provided P&P by today. | Umana Rafiq (P&P) | 2016-01-11
|  | PR will submitted by today | Abdullah Abu Saleh | 2016-01-11
10 | Hathazari_P | New location will be explored by 20-Jan-16. | Kazi Shawon (Admin) | 20-Jan-16.
11 | Chokoria_P | New location will be explored by 20-Jan-16. | Kazi Shawon (Admin) | 20-Jan-16.
12 | Cox's Bazar_P | We will BSCL office as a SCL PoP & Power system is not required for this site as we will use BSCL power System. | Md. Adbul Jabbar Kabir (OM-2) | 1-Feb-16.