## Sheet1
Internal Meeting
Date |  | 2016-01-08
Location |  | 2nd Floor, NOC meeting Room
Meeting Title |  | Weekly Meeting
Department |  | IIG & ITC server Team
Participants |  | 1. Md. Samiul Bashar , 2. Muntasir Khan, 3. Md. Shohel Rana, 4. Sadia safwat 5. Subrata Sarker
Sl No. | Stakeholder | Agenda | Discussion | Action Owner | Start Date | Deadline | Status | Remarks
1 | IIG & ITC | MRTG Server Shift | New MRTG server has been made. Need to All clinet and Internal connectivity MRTG graph shift from old to new MRTG. | Subrata Sarker | 2016-01-06 | 2016-05-08 | ongoing
2 | IIG | IIG NQM (PRTG) | New PRTG Motitoring tool has been ready to use | Subrata Sarker | 2016-01-06 | 31/7/2016 | closed
3 | IIG & ITC | NSTM (Netflow Analyzer) | Net flow analyzer has been sucesfully installed. Need testing more | Subrata Sarker | 2016-01-06 | 30/08/2016 | ongoing
4 | IIG & ITC | Log Analyser | Sys log Fully Installed | Subrata Sarker |  |  | closed
5 | IIG | Wiki | wiki portal has been installed | Subrata Sarker |  |  | closed
6 | IIG & ITC | Smoke Ping | Need to established | Muntasir Khan |  |  | closed
7 | IIG | DNS | New DNS has been made. Need to dovelopp more so that clinet can also use this server | Md. Shohel Rana | 2016-01-06 | 30/08/2016 | ongoing
8 | IIG & ITC | Cisco Prime Infrastructure | We have dowloaded Cisco Prime Infrastructure. Need to analysis to installed to our device | Md. Shohel Rana & Subrata sarker | 2016-01-06 | 30/08/2017 | ongoing