## Sheet1
Departmental Meeting - Power & Project
Date | 2016-07-29 |  | Time | 10:00 AM - 12:00 PM
Location | L5, Khan Sons Meeting Room
Attendees | Ashok Kumar, M. Alimuzzaman, Rowfut Tafsiri, Toufiq Zaman, Ashim Roy, Shaikhul Islam, Tousif zaman, Saibal Saha, Ishtyaq Rahman khan, Nasir Uddin Khan, Nitu Islam, Umana Rafiq, Tasneem Maksud
Sl. No. | Agenda | Description | Responsible | Timeline | Remarks
1 | Technical Specifications | Submit the Technical specifications that have been prepared so far. | Ashim Roy, Shaikhul Islam & Ishtyaq Rahman | 2016-08-12
2 | Yearly Work Update | Review the prepared Yearly Forecast update within Wednesday | Mubasser Hossain and Rubel Khan | 2016-08-15
3 | Deliver necessary docments to all the sites | Accumulate all the necessary documents for each site i.e. Single Line Diagram, AutoCAD and other documents (if required). The documents will be presereved at respective sites. | Kowshiq Mushfirq-Ur-Rahman and Umana Rafiq | 2016-08-31
4 | Training Materials | Materials for training purpose will be prepared within 17th August | Ashok Kumar & Ashim Roy | 2016-08-17
5 | Regarding Vendor assignment | This has been decided that from now on Partner Management team must be notified though mail before assigning a vendor for a work. M. Alimuzzaman will communicate with vendor for this purpose. | Project team | Immediate Action
6 | Rergarding New Asset delivery | This has been decided that from now on Inventroy concern person will notify Partner Management team as soon as a new material is delivered to warehouse as per PO. | Tousif Zaman and Partner Management team | Immediate Action