## Sheet1
Cross-Functional Meeting between O&M (PGCB) and P&P
Date | 2016-08-04 |  | Time | 3:30PM - 4:00PM
Location | L2, NOC Meeting Room, Khan Sons Building
Invitees | Abdullah Saleh, Sayda Kamrun Jahan Ripa, Ashok Kumar, Umana Rafiq
Sl. No. | Agenda | Description | Responsible |  | Timeline | Remarks
1 | Regarding PGCB space expansion issue | PGCB team will apply for space expansion for Noapara and Shirajgonj. P&P team can upgrade the power system accordingly | Ashok Kumar (P&P) , Abdullah Saleh (O&M) |  | Open
3 | Dhaka-Benapole DWDM expansion | During this phase of project no DWDM device wll be installed at any PGCB. On the next phase of this project ZTE devices will be swapped with Huawei Device at Bogra and Khulna PGCB. | Abdullah Saleh (O&M-PGCB) |  | Open