## Sheet1
Meeting Minutes
Cross departmental Meeting IT with Power & Project
August -7, 2016.
Attendees
· Md Musleh Uddin (P&P)
· Md Rubel Khan (P&P)
· Md Toufiq Zaman (P&P)
· Ziaul Hoque (IT)
­­
Sl | Agenda Item | Discussion / Decision / Proposal | Responsible | Timeline
1 | Ticket Raised issue | For any kinds of IT support need to raise a Ticket and IT will response ASAP. | P&P | From now
2 | Sub-Folder Issue at file server | SCL user have to sincerely acknowledge about sub folder and folders name. | P&P | From Now
Folder name and path should be short, at backup time if folder path as well as folder name found too long then it generates an error
3 | .exe file at file server | IT will provide .exe file name and location then P&P confirm us it will exists or not and after getting confirmation IT will delete it. | P&P | August 12 ,2016
4 | Admin Permission for laptop | If any Admin permission is required for a user’s then need a mail with concerning HOD | P&P | From now
5 | Space need in file server | Power & Project need more space in file server. They store here Image, auto-cad drawing and other important DOC which is required for site offices. | IT | August 15 2016
IT will informed them about more space in file server after discussed.
6 | Mail Quota in mail server | IT will provide a general guideline about how to mail Archive, and their mail Quota will be 2 GB Max. This will be applicable after archive their mail, To archive their mail they will take one week after receiving the guideline. | P&P, IT | IT will provide guideline within 10 August 2016 and to archive mail P&P will take one week (18.08.2016)
7 | Mail account delete from mail server. | A user list will provide P&P who leave from SCL P&P department and IT will delete mentioned user’s mail from mail server. IT will take one working day to delete it after getting the user name from P&P. | P&P , IT | P&P will mail us the name within August 12, 2016 .after receiving the confirmation mail from P&P, IT will takes one working day to delete the mail account .