## Sheet1
Minutes of Meeting
Date |  | 2017-06-06
Location |  | TK Bhaban
Meeting Title |  | DHK-CTG Airtel to Robi fiber swapping
Participants |  | 1. Mr. Abdul Jabbar Kabir 2. Mr. Yasir A Mabud 3. Mr. Farhan Solaiman 4. Mr. Muhitur Rahman Shuvo 5. Mr. Mostafiz Rahman 6. Mr. Papon Dey 7. Mr. MD. Shariful Islam 8. Mr. Ali Murtoza Khan 9. MS.Sarjana Jahan Chowdhury
SI | Agenda Item | Discussion | Responsible Concern | Deadline
1 | KMZ & Drawing to CRA | Implementation team will provide the surveyed area for HDD in KMZ & also the drawing of survey report to Mr. Mostafiz(CRA). | Mr. Papon Dey | 2017-06-06
2 | Approval from CRA | Due to the urgency & high priority, CRA will allow project team the comfort zone of working with verbal permission. Also Mr. Rubayet (CRA) will be available throughout the whole working procedure for any support. | Mr. Mostafiz & Mr. Rubayet | 2017-07-06
3 | As built drawing collection | Need to collect the as buit drawing of UG route of BTCL,GP, ROBI,Banglalink before HDD. | Robi-Mr. Yasir A Mabud BTCL, GP, Banglalink- Mr. Muhitur Rahman Shuvo | 2017-07-06
4 | Project estimation & PR | Project Estimation will be provided by implementation team & PR will be raised by O&M | Mr. Papon Dey(UG_Implementation) & MS. Sarjana Jahan Chowdhury(O&M-2) | 2017-06-06
5 | Planning | Planning team will provide the whole plan of connectivity of 7 PoPs including Paltan Pop & Akhteruzzaman Pop connectivity | Mr. Arifinul Karim | 2017-06-06
6 | Implementation work | Implementation team will start mobilizing the machineries for HDD within tomorrow in several segment areas. | Mr. Muhitur Rahman Shuvo | 2017-07-06