## Sheet1
Meeting Minutes
POP project
Date |  | 17.08.16
Location |  | Khansons (2nd floor outer meeting room)
Meeting Title |  | POP status and upcoming requirements
Agenda |  | Follow up and Catch up on various tasks
Participants |  | OM-2 |  | Abdul Jabbar Kabir, Baniah Nowroz Tilova, Nityananda Ghosh Piash, Abir Hasan
|  | Planning |  | Prianka Datta Suma, Md. Azizur Rahman Shumon, Arifinul Karim
|  | Implementation OH |  | Ibrahim Sharif
|  | IT |  | Ziaul Hoque
|  | IIG |  | Md. Niamul Bashir Talukder, Md. Samiul Bashar
|  | P&P |  | Musleh Uddin, Kowshik Mushfiqur Rahman
|  | SCM |  | Mir Moniruzzaman
|  | Implementation |  | Ehsan Karim, Mohib Ullah, Mustafa Shahinul Haque
SI | POP NAME |  |  | AGENDA | RESPONSIBLE PERSON (SCL/VENDOR) | DEADLINE | STATUS | REMARKS
1 | Palton |  |  | Generator installation | Ashok Kumar Biswas | 28.09.16
2 | Savar |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 20.08.16
3 | Tangail |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 20.08.16
4 | Shirajgonj |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 20.08.16
|  |  |  | Inverter Installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 22.08.16
5 | Bogra |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16
|  |  |  | PDB Load increment from 10 kw to 34 kw | Kazi Shawon / Md. Kamal Uddin | 21.08.16 |  | PDB workers are on strike.
|  |  |  | Generator installation | Kowshik Mushfiqur Rahman | 19.08.16
|  |  |  | AVR installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 24.08.16 |  | Vendor delivery pending
6 | Naogaon |  |  | Sanction Load doc. Of REB | Kazi Shawon | 20.08.16
|  |  |  | Inverter Installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 26.08.16 |  | Vendor delivery pending
7 | Rajshahi |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash | 09.08.16 | Pending at UG | UG to vertical splicing required
|  |  |  | Sanction Load doc. Of REB | Kazi Shawon | 20.08.16
8 | Natore |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash |  | NOK | Dependency on UG (after cable blowing vertical will be done)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Inverter Installation | Mr. Fazlu & Ashok Kumar | 28.08.16 |  | Vendor delivery pending
9 | Kustia |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Generator room Readiness | Kazi Shawon / Shipon | 19.08.16 | On going | Room readiness done. Gate pending.
|  |  |  | Generator installation | Mr. Arif & Ashok Kumar | 19.08.16
|  |  |  | AVR installation | Mr. Fazlu & Ashok Kumar | 28.08.16 |  | Vendor delivery pending
10 | Jheniadaha |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Inverter Installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 28.08.16 |  | Vendor delivery pending
| Jessore |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Generator room Readiness | Kazi Shawon / Md. Kamal Uddin | 19.08.16 |  | Gate pending
|  |  |  | Exhaust Fan Installation | Kazi Shawon / Md. Kamal Uddin / Mostafa Kamal |  |  | Not required as there is no proper space to place the exhaust fan (water can enter inside through exhaust fan space), verbally confirmed by Mr. Ashok
|  |  |  | AVR installation | Mr. Fazlu & Ashok Kumar | 24.08.16 |  | Vendor delivery pending
|  |  |  | Inverter Installation | Mr. Fazlu & Ashok Kumar | 24.08.16 |  | Vendor delivery pending
12 | Khulna |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | PDB Load increment from 25 kw to 34 kw | Kazi Shawon / Tayamun Centre Authority | 3 month |  | Building Authority will install new sub-station
|  |  |  | AVR installation | Mr. Fazlu & Ashok Kumar | 22.08.16 |  | Vendor delivery pending
| Benapole |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan | 21.08.16 |  | Pending at SCM
|  |  |  | Grounding Cable dreassing (inside Power room) | Mostafa Kamal / Nayan (United Sysnet) |  |  | a ladder will be installed by P&P
|  |  |  | Generator room Readiness | Kazi Shawon / Depongkor | 22.08.16 | On going | Room readiness done. Gate pending
|  |  |  | Generator installation | Mr. Arif & Kowshik Mushfiqur Rahman | 20.08.16
|  |  |  | AVR installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 26.08.16 |  | Vendor delivery pending
|  |  |  | Inverter Installation | Mr. Fazlu & Kowshik Mushfiqur Rahman | 26.08.16 |  | Vendor delivery pending
14 | All POP |  |  | POP vertical cable readiness | Md. Abdullah Al. Mamun, Sharif Abul Kalam Azad, S.H. Zaman |  |  | The responsibility for POP vertical readiness will be based on, if UG will reach before ODF termination, they will keep estimated amount fiber in drum inside POP without cutting then responsible team for vertical and ODF termination will take this fiber for ODF termination. If UG team reach later i.e after ODF temination, then they will find estimated fiber loop inside POP (estimated fiber length will be shared by UG before) from ODF which will take inside Hand hole with fiber cut
15 | Barisal |  |  | UG readiness | Sharif Abul Kalam Azad |  |  | Cable blowing
|  |  |  | T-joint | Sharif Abul Kalam Azad |  |  | UG backbone readiness
|  |  |  | High level planning | Prianka Datta
|  |  |  | Passive Planning | Prianka Datta
16 | All POP |  |  | Handover process | POP team members |  |  | After full handover of any POP (from one team to another) snag issues or any kind of observation should be raised within 48 hours otherwise receiving team will be considered responsible for that snag. Before going to do work in any pop every team has to circulate an email regarding work schedule i.e. time and date of doing work should be shared through mail 48 hours before visiting that pop for work.
17 | DHK-CTG-COX |  |  | High level planning | Arifinul Karim | 21.08.16
18 | DHK-CTG-COX |  |  | Requirement details | Arifinul Karim | 21.08.16 |  | Email should contain location, latitude & longitude, NTTN load, total sft required, POP type, radius and every details related to DHK-CTG-COX route.
SI | Agenda |  | POP location
1 | Dhaka-Benapole |  | Summit Center
Banani (New Mohakhali)
Savar (Existing)
Tangail (Existing)
Shirajgonj (new)
Bogra (Expansion)
Naoga (new)
Rajshahi (Existing)
Nator (new)
Kushtia (Expansion)
Jhinaidha (Expansion)
Jessore (Expansion)
Khulna (Expansion)
Benapole (Expansion)
2 | DHK-CTG-COX |  | Vulta
Bhairab
B. Baria
Debidder
Comilla
Chandpur
Laxmipur
Noakhali
Feni
Heyako Bazar
Hathazari
GEC CTG new
Satkania
Chokoria
Cox-bazar