## Urgent pop expansion status
POP SUMMARY
Total Sites Till Date | Feasibility Check | Survey Ongoing |  | After Survey Status |  |  | POP Readiness Ongoing |  | DOHS sites (CRF is working for permission) | Ready for Service | Remarks
|  | Info and MKT | MKT | Go Call for install POP (Info and MKT) | Go Call for install POP (MKT) | Halt (MKT) | Info and MKT | MKT
47 | 8 | 5 | 0 | 2 | 5 | 10 | 4 | 0 | 3 | 10
| Client Information ( Before POP Ready)- Filled By Marketing | [8 empty] | POP Readyness Information ( PAD & P&P)
Sl. No. | Required POP Location | District | Thana | Client Name | Client Proposed Lat | Client Proposed Long | Client Proposed Address | MKT Request | MKT Feedback- Final Call for POP Readyness | POP Type | POP Satus | POP Lat | POP Long | POP Address | Client Serve By | Tentative POP readyness (Days) | POP On air Date | Remarks ( PAD & P&P)
1 | Panghsa, Rajbari | Rajbari |  | Web Link | 23.7883 | 89.4169 |  | 2017-05-28 | Requesting you to proceed for implementation,we are working for the work order,Client will issue the work order on 20th July 2017 | E.Co | Ready for install sw | 23.7884 | 89.4167 |  | Edotco | 10 |  | Nearest Robi site 200 m far RJPNG01. Waiting for work order from MKT
2 | Tulshighat,Kashinath high school,Gaibandha high way,Gaibandha | Gaibandha |  | Web Link | 25.3143 | 89.4813 |  | 2017-05-28 | Client did not confirm the work order till now | E.Co | Ready for install sw | 25.3149 | 89.4816 |  | Edotco | 10 |  | Nearest Robi site 200 m far GBSDR04.Waiting for work order from MKT
3 | Mili Plaza,Kulaura bazar,Moulovibazar,Sylhet | Sylhet |  | Web Link | 24.5262 | 92.0363 |  | 2017-05-28 | Requesting you to proceed for implementation,we are working for the work order.received work order . | E.Co | POP on air | 24.5256 | 92.0368 |  | Edotco | 10 |  | Nearest Robi site 200 m far MBKLR01. client provided
4 | Shathibari,Mithapukur,Rangpur | Rangpur |  | Web Link | 25.5392 | 89.2841 |  | 2017-05-28 | Client did not confirm the work order till now. Hault | E.Co | Ready for install sw | 25.5712 | 89.2747 |  | Edotco | 10 |  | Nearest Robi site 3.8 km far RPMTH01.Waiting for work order from MKT
5 | Madhupur Upazila | Tangail | [5 empty] | 2017-05-28 | We are working for the work order |  | POP on air | 24.6047 | 90.0275 | Modhupur Tangile |  | 60 |  | POP Ready. SCL have switch
6 | Kesobpur, Jessore | Jessore |  | Amber IT |  |  |  | 2017-05-28 | Client did not confirm the work order till now | Info | POP readiness | 22.9061 | 89.2157 | Village –Upzala Office Para, Post/P.S./Upazila- Keshobpur , Dist- Jessore ; Md. Julfekir Cell-01710749406 |  | 30 |  | Legal documents process ongoing
7 | Indira Road,Sorupkathi | Pirojpur |  | WBDN | 22°45'8.04"N | 90° 5'15.71"E |  | 2017-05-28 | Client is highly interested to take connetciivty | Info | Approval process | 22.7452 | 90.0989 | Spark Computer,2nd Floor,Shorupkathi,Necharabad |  | 30 |  | Legal documents process ongoing
8 | Mawa, Louhojong, Munshigonj | Munshigonj |  | Zip Net | 23°27'59.08"N | 90°16'49.38"E |  | 2017-05-28 | Requesting you to proceed for implementation,we are working for the work order | Info | Survey on going |  |  |  |  | 30 |  | Waiting for PAD go-call
9 | Salta bazar(Near Grameen bank),Salta,Faridpur | Faridpur |  | Web Link |  |  |  | 2017-05-28 | Client did not confirm the work order till now.Halt | Info | Halt | 23.4375 | 89.7678 | Vai vai Traders, School Road, Saltha, Faridpur. |  | 30 |  | Infosakar Pop. Nomaly timeline on going. MKT-Halt after survey
10 | Ratandia bazar,Kalukhali,Rajbari. | Rajbari |  | Web Link | 23.7657 | 89.4864 |  | 2017-05-28 | Client did not confirm the work order till now | Info | Survey on going | 23.7591 | 89.5009 | Padma Rural Devlopment foundation,Kalukhali Bus stand |  | 30 |  | Infosakar Pop. Nomaly timeline on going
11 | New dutta market,(Near oangsha powrashova)Maguradangi road,Pangsha | Rajbari |  | Web Link | 23.7883 | 89.4169 |  | 2017-05-28 | For SL No. 1& 11 pop is same .received work order . | Info | Ready for install sw | 23.7884 | 89.4167 |  |  | 30 |  | Waiting for MD Sir's Approval
12 | Sreebardi, Sherpur | Sherpur |  | Amber IT |  |  |  | 2017-05-28 | Halt |  | Halt |  |  |  |  | 30 |  | Marketing is not confrim yet. Halt before survey
13 | Bhola Sadar Upazila | Bhola | [5 empty] | 2017-05-28 | Client is eagerly waiting for the connetivity | Info | Plan provide pending | 22.‎67772 | 90.6449 | Road: Mushalman Para, Union Bapta, Bhola |  | 30 |  | POP Ready for infosarkar. BB not ready
14 | Char Fasson Upazila, Bhola | Bhola | [5 empty] | 2017-05-28 | Client is eagerly waiting for the connetivity | Info | Survey on going |  |  |  |  | 30 |  | Waiting for PAD go-call. BB not ready
15 | Sreepur Upazila, Gazipur | Gazipur | [5 empty] | 2017-05-28 |  | Info | POP readiness | 24.1986 | 90.4775 | Nurul Islam Khan Complex, Sreepur, Gazipur |  | 30 |  | Waiting for MD Sir's Approval
16 | Madhabpur Upazila | Habiganj | [5 empty] | 2017-05-28 |  | Info | POP selection | 24.6054 | 90.0278 | Al-Hera Market, Madhupur |  | 30 |  | Waiting for PAD go-call
17 | Shyamnagar Upazila, Shatkhira | Shatkhira | [5 empty] | 2017-05-28 |  | Info | Survey on going |  |  |  |  | 30 |  | Survey ongoing
18 | Khilkhet, Dhaka | Dhaka | [5 empty] | 2017-05-28 |  | Info | Survey on going |  |  |  |  | 30 |  | Survey ongoing
19 | Bauphal, Patuakhali | Patuakhali | [5 empty] | 2017-05-28 | Client did not confirm the work order till now | SCL | Halt |  |  |  |  | 10 |  | Request for survey. Halt before survey
20 | DashMina, Patuakhali | Patuakhali | [5 empty] | 2017-05-28 | Client did not confirm the work order till now. | SCL | POP on air |  |  |  |  | 10 |  | Site ready
21 | Dupchachia Bogra | Bogra |  | HN Telecom |  | 24.8799 |  | 2017-05-28 | We are working for the work order | SCL MKT | POP selection | 24.8783 | 89.1753 | Zila Model School, Dupchachia, Bogra |  | 30 |  | Plan should provided as soon as posible
22 | Companygonj, Sylhet | Sylhet | [5 empty] | 2017-05-28 | We are working for the work order |  | Halt |  |  |  |  | 30 |  | companigonj should ready after MKT go call
23 | Jaintiapur Upazila, Sylhet | Sylhet | [5 empty] | 2017-05-28 |  |  | POP readiness |  |  |  |  | 30 |  | Jayentapur Power system shound upgrade. Info Phase-2 POP
24 | Chittagong Fatikchari | Chittagong |  | Zip Net | 22°41'13.79"N | 91°47'28.65"E |  | 2017-05-28 | Working on it |  | Request for feasibility |  |  |  |  | 30 |  | Request for survey.
25 | Vulta | Narangonj |  | Metro Net | 23.7846 | 90.5664 |  | 2017-05-28 | Client will issue the work order shortly |  | Approval process for co-location |  |  |  |  | 30 |  | MKT will arrange co-location facility with BracNet/Amber IT
26 | Balua,Chomohoni | Noakhali |  | Amber IT |  |  |  | 2017-05-28 | hault |  | Halt |  |  |  |  | 30 |  | MKT will arrange co-location facility with BracNet/Zip Net
27 | Taherpur,Rajshahi | Rajshahi |  | Zip Net |  |  |  | 2017-05-28 | We are working for the work order |  | Approval process | 24.523 | 88.8465 | Khan Market, Taherpur, Rajshahi |  | 30 |  | Waiting for MD Sir's Approval. Plan should provided
28 | Kalkini,Madaripur | Madaripur |  | Asia Pacific | 23.0737 | 90.233 |  | 2017-05-28 | We are working for the work order |  | Approval process | 23.0734 | 90.2425 | R.M. Plaza, Holding no.- 128 Village -Chor Bibhagdi, Road- High School Road, Aria- Puran Bazar, Post/P.S./Upazila- Kalkini, Dist- Madaripur |  | 30 |  | Waiting for MD Sir's Approval
29 | Madargonj yatimkhana | Gaibandha |  | Web Link | 25.4276 | 89.3789 |  | 2017-05-28 | halt |  | Halt |  |  |  |  | 30 |  | Site survey will be started after marketing go call
30 | Baraiyarhat bus Terminal,Ctg | Chittagong |  | Web Link | 22.8934 | 91.5346 |  | 2017-05-28 | halt |  | Halt |  |  |  |  | 30 |  | we can serve is by GP site
31 | Debidawar,Comilla | Comilla |  | Manor IT | 22°41'13.79"N, | 91°47'28.65"E |  | 2017-05-28 | Within 1st week after Eid,POP is required to establish.Otherwise client cancell the requirement |  | POP on air | 23.6019 | 90.9845 | Village Ismahail Manson, House no-46 ,Govment College Road, , Post/P.S./Upazila- Debidawar , Dist- Comilla |  | 30 |  | Site ready for client connectivity
32 | Ramghar,Khagrachari | Khagrachari | [5 empty] | 2017-05-28 | halt |  | Halt | 22.9976 | 91.7358 | Master Para, Ramgarh, Khagrachori. |  | 30 |  | Survey done.Others works will be started after marketing go-call. Halt after survey
33 | Atrai Upazila | Naogaon | [5 empty] | 2017-05-28 | halt |  | Halt |  |  |  |  | 30 |  | Survey done.Others works will be started after marketing go-call.Halt after survey
34 | Chandina Upazila | Comilla | [5 empty] | 2017-05-28 | halt |  | Halt |  |  |  |  | 30 |  | Halt after survey
35 | Mirpur DHOS | Dhaka | [5 empty] | 2017-05-28 |  |  | CRA |  |  |  |  | 30
36 | Mohakhali DHOS | Dhaka | [5 empty] | 2017-05-28 |  |  | CRA |  |  |  |  | 30
37 | Nikaton | Dhaka | [5 empty] | 2017-05-28 |  |  | CRA |  |  |  |  | 30
38 | Nikunjo | Dhaka | [5 empty] | 2017-05-28 |  |  | Approval process for co-location |  |  |  |  | 30 |  | Survey done. Next process will start at BOL colocation POP
39 | Kaliganj,Satkhira | Satkhira |  | Circle Network | 22.5164 | 89.0179 |  | 2017-06-09 | Received work order already. |  | POP on air | 22.5163 | 89.0188 | Circle Network, Nalta, Kaliganj, Satkhira |  | 30 |  | Site will be up by 14-Jul-17
40 | Bhuapur, Tangail | Tangail |  | TryCatch | 24°27'49.40"N | 89°52'21.61"E |  | 2017-06-09 | Received work order. |  | POP on air | 24.4621 | 89.8724 | Mourin Super Market,Bhuapur Bazar,Tangail |  | 30 |  | Site will be up by 12-Jul-17
41 | Nilphamari Sadar | Nilphamari | Nilphamari Sadar | Broad Band Telecom Services Limited | 25.8471 | 88.8733 |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 25.8615 | 88.8676 | Uttara Export Processing Zone, Nilphamari, Represented by its Project Director, Uttara EPZ, Shangalshi, Nilphamari. Ph # 01713-201068 |  |  |  | NPSDR03.Not scl site. From propose site to client location 2km away
42 | Tulshigat Kashinath High School,Gaibandha Hwy,Gaibandha. | Gaibandha |  | Web Link Communications Ltd | 25.3143 | 89.4813 |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 25.3149 | 89.4816 |  |  |  |  | GBSDR04 . Scl site. From propose site to client location 200m away
43 | Sarishabari, Jamalpur | Jamalpur |  | ISN | 24°45'56"N | 89°50'29"E |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 24.7692 | 89.8404 |  |  |  |  | JPSSB02. Not scl site. From propose site to client location 700m away
44 | Dumuriya Bazar, Khulna | Khulna |  | S S ali | 22.704740, | 89.4378 |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 22.7042 | 89.4327 | GopalMondol&SubodMondol01918016854,01913794465Khatianno.SA858,DagnoRS.4342(new),3150(old),JLNo.188,Mouza.Kalikapur,Union&Post:Sorappur,PS&Upazila:Dumuria,Dist:Khulna |  |  |  | KHDMR04. Not scl site. From propose site to client location 800m away
45 | Chuknagar, Khulna | Khulna |  | S S ali | 22.8406 | 89.2958 |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 22.84 | 89.2964 | S.MAbdulKayun,S/o:Late-S.MAbdulWahhab,BuildingofMr.AbdulKayum,ChuknagarBazar,Khulna.Ph#0171-573073 |  |  |  | KHDMR01. Not scl site. From propose site to client location 1 km away
46 | Chalna Bazar/Bandor , Khulna | Khulna |  | S S ali | 22.6029 | 89.5224 |  | 2017-07-13 | Client is eager to provide work order | Info POP | Request for feasibility | 22.6009 | 89.5182 |  |  |  |  | Infosarkar Phase 2 pop existing. From pop to client location 1.8 km away
47 | Gopalgong | Gopalgonj |  | S S ali | 22.9501 | 89.7794 |  | 2017-07-13 | Client is eager to provide work order | E.Co | Request for feasibility | 22.9502 | 89.7794 | Noni Gopal Biswas, Vill: Gurada, Post: Mollahat, P S: Mollahat, Dist: Bagerhat, 01713 900533, 01933 900533 |  |  |  | BGMLH09. Not scl site. From propose site to client location 100 m away