## Sheet1
Meeting Minutes
POP project
Date |  | 24.08.16
Location |  | Khansons (2nd floor outer meeting room)
Meeting Title |  | POP status and upcoming requirements
Agenda |  | Follow up and Catch up on various tasks
Participants |  | OM-2 |  | Baniah Nowroz Tilova, Nityananda Ghosh Piash, Abir Hasan
|  | OM-1 |  | Md. Arafat Bin Islam
|  | Planning |  | Prianka Datta Suma, Md. Azizur Rahman Shumon
|  | UG |  | Sharif Abul Kalam Azad
|  | IT |  | Ziaul Hoque
|  | IIG |  | Md. Niamul Bashir Talukder
|  | SCM |  | Rezaul Haque
|  | Implementation |  | Ehsan Karim, Mustafa Shahinul Haque
SI | POP NAME |  |  | AGENDA | RESPONSIBLE PERSON (SCL/VENDOR) | DEADLINE | STATUS | REMARKS
1 | Palton |  |  | Generator installation | Ashok Kumar Biswas | 28.09.16
2 | Savar |  |  | Savar to Tangail pop link | S.K Abir Hasan | 26.08.16 |  | Savar POP - Kabirpur PGCB -Tangail PGCB -Tangail POP
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 26.08.16
3 | Tangail |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 26.08.16
4 | Shirajgonj |  |  | Shirajgong to Tangail POP UG link readiness | Sharif Abul Kalam Azad | 25.08.16 |  | Tangail POP - Tangail BTCL - Shirajgonj BTCL- Shirajgonj POP (fiber splicing)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Sanction Load doc. Of REB | Kazi Sifatul Kabir Shawon | 26.08.16
5 | Bogra |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | PDB Load increment from 10 kw to 34 kw | Kazi Shawon / Md. Kamal Uddin | 21.08.16 | pending
6 | Naogaon |  |  | Roxtec installation | Roxtec installation
|  |  |  | Sanction Load doc. Of REB | Kazi Shawon | 26.08.16
7 | Rajshahi |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Rajshahi- Naogaon UG link readiness | Sharif Abul Kalam Azad | 26.08.16 |  | 1500 m cable blowing, 1 HH, 1 SP pending
|  |  |  | Rajshahi- Natore UG link readiness | Sharif Abul Kalam Azad | 26.08.17 |  | 3 km cable blowing, 2 HH, 12SP pending
|  |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash | 09.08.16 | Pending at UG | UG to vertical splicing required
|  |  |  | Sanction Load doc. Of REB | Kazi Shawon | 26.08.16
8 | Natore |  |  | Vertical | Mr. Shujon, Abir Hasan & Nityananda Ghosh Piash |  | NOK | Dependency on UG (after cable blowing vertical will be done)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
9 | Kustia |  |  | Kushtia- Natore UG link readiness | Sharif Abul Kalam Azad | 25.08.16 |  | 1 SP pending (permission issue)
|  |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
10 | Jheniadaha |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
11 | Jessore |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
12 | Khulna |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | PDB Load increment from 25 kw to 34 kw | Kazi Shawon / Tayamun Centre Authority | 3 month |  | Building Authority will install new sub-station
13 | Benapole |  |  | Roxtec installation | Mr. Fazlu, Shah Mohammad Asif & Abir Hasan |  |  | Pending at SCM
|  |  |  | Grounding Cable dreassing (inside Power room) | Mostafa Kamal / Nayan (United Sysnet) |  |  | a ladder will be installed by P&P
|  |  |  | Generator room Readiness | Kazi Shawon / Depongkor | 22.08.16 | On going | Room readiness done. Gate pending
14 | All POP |  |  | POP vertical cable readiness | Md. Abdullah Al. Mamun, Sharif Abul Kalam Azad, S.H. Zaman |  |  | The responsibility for POP vertical readiness will be based on, if UG will reach before ODF termination, they will keep estimated amount fiber in drum inside POP without cutting then responsible team for vertical and ODF termination will take this fiber for ODF termination. If UG team reach later i.e after ODF temination, then they will find estimated fiber loop inside POP (estimated fiber length will be shared by UG before) from ODF which will take inside Hand hole with fiber cut
15 | All POP |  |  | Handover process | POP team members |  |  | After full handover of any POP (from one team to another) snag issues or any kind of observation should be raised within 48 hours otherwise receiving team will be considered responsible for that snag. Before going to do work in any pop every team has to circulate an email regarding work schedule i.e. time and date of doing work should be shared through mail 48 hours before visiting that pop for work.
SI | Agenda |  | POP location
1 | Dhaka-Benapole |  | Summit Center
Banani (New Mohakhali)
Savar (Existing)
Tangail (Existing)
Shirajgonj (new)
Bogra (Expansion)
Naoga (new)
Rajshahi (Existing)
Nator (new)
Kushtia (Expansion)
Jhinaidha (Expansion)
Jessore (Expansion)
Khulna (Expansion)
Benapole (Expansion)
2 | DHK-CTG-COX |  | Vulta
Bhairab
B. Baria
Debidder
Comilla
Chandpur
Laxmipur
Noakhali
Feni
Heyako Bazar
Hathazari
GEC CTG new
Satkania
Chokoria
Cox-bazar