## Sheet1
Meeting Minutes
Vendor Meeting at Rajshahi SC
Date | 22.11.2017
Location | Rajshahi Sc office
Meeting Title | Monthly Followup Meeting
Agenda | Follow up and Catch up on various tasks
Participants | Md. Sabbir Ferdous, Mr. Limon Chandra, Mst. Shamima Nasrin, Mr. Tutul Mollah, Mr. Abu Sayeed
SI | Agenda Item | Discussion | Responsible Concern | Deadline | SCL Feedbcak
1 | PM | Due to PDB activity Chapai Vendor team couldn't be assigned for PM right now but Rajshahi & Sirajganj team are free. They can start PM from Sunday. | Mr. Mahbub & Mr. Toufik (SCL Concern), Mr. Sayed (Vendor Concern) | Continue Process. Feedback should be given every Monday & shown in Weekly Meeting of SCL.
2 | Messenger Link Maintenance with Messenger Fiber, Also 6F & 12F Normal Fiber | Vendor team alligned with this. | Mr. Jahid (RSL) will take care of this. Update should be given on Monthly Incident basis. | Continue Process. Feedback should be given every Month.
3 | Messenger Link Shifting to Replaced Pole & Newly Installed Pole | 1. In case of pole replacing Vendor will provide related accessories to shift the Messenger fiber. 2. In case of newly Installed pole, we will feedback vendor after discussing with Musabbir Vai. | Sabbir | Within Next Week, I will provide feedback.
4 | HSSE | As per vendor feedback, they are using Safety equipment. In our previous sudden visit we didn't found proper safety equipment. But they have told that they will properly use the safety equipment. | Mr. Sayed | Continue Process.
5 | Dismantled Fiber Return | Vendor Concern have sent some fiber from Sirajganj, Mr. Tutul will discuss with SCM regarding remaining fiber returning. | Md. Abdur Sobur Mollah | Requesting Feedback within 30-11-2017.
6
7
8