## BCN_24-11-17
Meeting Minutes
Vendor Meeting at Rajshahi SC
Date | 24.11.2017
Location | Rajshahi Sc office
Meeting Title | Followup Meeting With Bandhan Cable Network
Agenda | Follow up and Catch up on various tasks
Participants | Md. Sabbir Ferdous, Mr. Mahbubul Haque, Mr. Limon Chandra, Mst. Shamima Nasrin, Mr. Sujon, Mr. Hafizul, Mr. Entaj
SI | Agenda Item | Discussion | Responsible Concern | Deadline | SCL Feedbcak
1 | Preventive Maintenance | Due to PDB activity & Drainage activity at Natore team couldn't be assigned for PM right now. They wil start PM when pole shifting & Drainage activity completed. Status should be shared in every Monday. | Mr. Mahbub & Mr. Toufik (SCL Concern), Mr. Sujon (Vendor Concern) | Continue Process. Feedback should be given every Monday & shown in Weekly Meeting of SCL.
2 | Hanging TJ Remove | Vendor team acknowledged about this issue. They will remove all the hanging TJs within 08-12-2017. | Mr. Jahid (RSL) will take care of this. First Update should be given on 01-12-2017. | 2017-08-12
3 | Team Member & Vehicle Shortage | Vendor team will recruit another Technician & a dedicated vehicle for Natore. | Sabbir | 2017-08-12
4 | HSSE | As per vendor feedback, they are using Safety equipment. In our previous visit we didn't found proper safety equipment. But they have told that they will properly use the safety equipment. | Sabbir | Continue Process.
5 | Activity in Viber Group | Vendor alligned with this. | Mr. Mahbub & Mr. Sujon | Continue Process.
6
7
8